Appendix W

Transition Milestones

Unified Communications & Voice Services – Lot 1, Lot 2, Lot 3

RFP NUMBER

6100039274

Transition Milestones

The following table includes a list of key required project milestones and delivery dates as applicable.  Milestone sue dates are as indicated below, unless otherwise agreed to by the Commonwealth in writing. Milestones include the completion of all tasks and deliverables associated with the milestone as described in this RFP.   The Earn Back period is thirty (30) calendar days from the Transition Milestone Due Date and applies to those Milestones indicated with “Y” in the Earn Back column.

Note: Milestones 14 through 17 are dependent on the successful completion of Milestones 1 through 13.

| Transition Planning and Management Milestones For the Transition Planning and Management Milestones, Offerors should assume a ten (10) business day period for the Commonwealth to review and respond for each iteration of a deliverable submission. This ten day period is included in the total time reflected in the Milestone Due Date. |
| --- |
| Milestone Number | Transition Milestone | Milestone Due Date | Acceptance Criteria | Milestone Credit | Earn Back | Dependency on Commonwealth |
| M-1 | Final Transition Plan | 30 calendar days from Contract Effective Date | Final transition plan and detailed project schedule established and accepted | $75,000 | N | Commonwealth review and approval |
| M-2 | Change Management Plan | 30 calendar days from Contract Effective Date | Final Change Management Plan due and accepted on or before the Milestone Due date | $25,000 | Y Earnback 75% | Commonwealth review and approval |
| M-3 | Service Asset & Configuration Management Plan | 30 calendar days from Contract Effective Date | Final Service Asset & Configuration Management Plan due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and approval |
| M-4 | Configuration Management Data Base Plan | 30 calendar days from Contract Effective Date | Final Configuration Management Data Base Plan due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-5 | Continuity of Operations / Emergency Response Plan | 30 calendar days from Contract Effective Date | Final Configuration Management Data Base Plan due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-6 | Service Delivery Implementation / Management Plans | 30 calendar days from Contract Effective Date | Final Service Delivery Implementation and Management Plans due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-7 | Order Process Implementation Plan | 30 calendar days from Contract Effective Date | Final Order Process Implementation Plan due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-8 | Marketing Plan | 45 calendar days from Contract Effective Date | Final Marketing Plan due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-9 | Training Plan / Training Materials | 45 calendar days from Contract Effective Date | Final Training Plan / Training Materials due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-10 | Service Desk Implementation and Management Plans | 45 calendar days from Contract Effective Date | Final Service Desk Implementation and Management Plans due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-11 | Ticket Escalation Process | 60 calendar days from Contract Effective Date | Final Ticket Escalation Process due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-12 | Feature Code List | 60 calendar days from Contract Effective Date | Final Feature Code List due and accepted on or before the Milestone Due date | 25,000 | Y Earnback 75% | Commonwealth review and acceptance |
| M-13 | Final Enterprise Process and Procedures Manual (ePPM) | 120 calendar days from Contract Effective Date | Final Enterprise Process and Procedures Manual (ePPM) due and accepted on or before the Milestone Due date | $25,000 | N | Commonwealth review and approval Access to current PPM documentation as available |
| Service Enablement Milestones For Service Enablement Milestones, acceptance will occur upon Commonwealth review and acceptance of the successful Offeror’s test plan and demonstration of service enablement. |
| Milestone Number | Transition Milestone | Milestone Due Date | Acceptance Criteria | Milestone Credit | Earn Back | Dependency on Commonwealth |
| M-14 | Service Desk Operational | 120 calendar days from Contract Effective Date | Service Desk available and accepted by the Commonwealth on or before the Milestone Due date | $250,000 | Y Earnback 100% | Commonwealth review and acceptance |
| M-15 | Unifed Communications & VoIP Services | 180 calendar days from Contract Effective Date | Services and deliverables as described in LOT 1 Unified Communications & VoIP Services and Support transitioned and accepted on or before Milestone Due date Services implemented, tested, and operational | $250,000 | N | Commonwealth review and approval |
| M-16 | Traditional Voice Services | 120 calendar days from Contract Effective Date | Services and deliverables as described in LOT 2 Traditional Voice Services and Support transitioned and accepted on or before Milestone Due date Services implemented, tested, and operational | $250,000 | Y Earnback 100% | Commonwealth review and approval |
| M-17 | PSTN Conferencing through Skype for Business | 120 calendar days from Contract Effective Date | Services and deliverables as described in LOT 3 PTSN Conferencing through Skype for Business and Support transitioned and accepted on or before Milestone Due date Services implemented, tested, and operational | $250,000 | Y Earnback 100% | Commonwealth review and approval |