REQUEST FOR PROPOSALS FOR

Technology Platform and Consumer Assistance Center for the Pennsylvania Health Insurance Exchange

ISSUING OFFICE

Pennsylvania Insurance Department

Bureau of Administration

1326 Strawberry Square

Harrisburg, Pennsylvania 17120

on behalf of

the Pennsylvania Health Insurance Exchange Authority

RFP NUMBER 6100048766

DATE OF ISSUANCE

August 19, 2019

REQUEST FOR PROPOSALS FOR

Technology Platform and Consumer Assistance Center for the Pennsylvania Health Insurance Exchange

TABLE OF CONTENTS

CALENDAR OF EVENTS	3

1.	GENERAL INFORMATION	4

2.	Proposal process & Requirements	11

3.	CRITERIA FOR SELECTION	22

4.	TECHNICAL SUBMITTAL – Response format	25

5.	technical requirements	37

6.	Timeline and Deliverables.	48

7.	COST SUBMITTAL	68

APPENDIX A:  TRADE SECRET/CONFIDENTIAL PROPRIETARY INFORMATION NOTICE	70

APPENDIX B:  REQUIREMENTS FOR NON-COMMONWEALTH HOSTED APPLICATIONS / SERVICES	71

APPENDIX C:  INFORMATION TECHNOLOGY POLICIES	75

APPENDIX D:  REQUIRED INTERFACES & SYSTEMS INTEGRATION	77

APPENDIX E:  STANDARD TERMS & CONDITIONS	80

APPENDIX F:  CUSTOMER SERVICE TRANSFORMATION STANDARDS	81

ATTACHMENT A:  PROPOSAL COVER SHEET	85

ATTACHMENT B:  COST SUBMITTAL FORM	86

ATTACHMENT C:  BUSINESS ASSOCIATE AGREEMENT	88

ATTACHMENT D:  SIGN-OFF DOCUMENT	96

ATTACHMENT E:  CLOUD USE CASE QUESTIONNAIRE	97

ATTACHMENT F: DRAFT SERVICE LEVEL AGREEMENTS AND ASSOCIATED LIQUIDATED DAMAGES	103

# CALENDAR OF EVENTS

The Commonwealth will make every effort to adhere to the following schedule:

| Activity | Responsibility | Date |
| --- | --- | --- |
| Deadline to submit Questions via email to mlapkowicz@pa.gov. | Offerors | 5:00 p.m. on September 9, 2019 |
| Answers to Potential Contractor questions posted to eMarketplace at http://www.emarketplace.state.pa.us/Search.aspx no later than this date. | Issuing Office | 5:00 p.m. on September 13, 2019 |
| Please monitor website for all communications regarding the RFP. | Offerors | Ongoing |
| eMailed proposals must be received at the email address mlapkowicz@pa.gov. | Offerors | 5:00 p.m. on September 16, 2019 |
| Presentations/Live Demonstration by Offerors, if required. | Offerors | Time TBD October 7-9, 2019 |

- GENERAL INFORMATION

  - Terminology and Acronyms

For the purposes of this RFP, the following terms and acronyms shall be defined as follows:

“ACA” – Patient Protection and Affordable Care Act.

“ACD” – Analyze, Configure and Deploy (see DDI)

“ADA” – Americans with Disabilities Act.

“APTC” – Advance Premium Tax Credit.

“Authority” – Pennsylvania Health Insurance Exchange Authority.

“BAFO” – Best and Final Offer.

“Base configuration” - the existing state of the Offeror’s platform as most recently deployed to support at least one SBE, prior to the issuance of this RFP, exclusive of any alteration, customization, re-configuration, or extension of the platform’s features, capabilities, or architecture necessary to fulfill the requirements of this RFP.

“Commonwealth” – Commonwealth of Pennsylvania.

“CRM” – Customer Relations Management.

“CMS” – United States Department of Health and Human Services, Centers for Medicare and Medicaid Services.

“CSR” – Cost-Sharing Reduction subsidies.

“Consumer assistance center” - the software, hardware, infrastructure, and human resources required to provide the consumer assistance functions detailed in Section 5, exclusive of the technology platform.

“DDI” – Design, Development, and Implementation.  Note, wherever DDI is used throughout this RFP, the real intent is to indicate “ACD” which means Analyze, Configure and Deploy.  Given that the Commonwealth only seeks proposals that offer an already-built, field-proven solution, the use of the terminology “Design, Development and Implementation” is not accurately reflective of the Commonwealth’s intent.  However, the term DDI has been used as it is a familiar term to many potential Offerors.  This term may also be used to describe customized interfaces or integration required in the future with external Commonwealth agencies, business partners, or federal entities.

“Department” – Pennsylvania Insurance Department.

“DGS” – Department of General Services.

“DHS” – Department of Human Services.

“DMI” – Data Matching Issues.

“EDI” – Electronic Data Interchange.

“Exchange” – State-Based Exchange.

“FDSH” – Federal Data Services Hub.

“FFE” – Federally-Facilitated Exchange.

“FTI” – Federal Tax Information.

“GUI” – Graphical User Interface.

“HHSDC” – Health and Human Service Delivery Center.

“HIPAA” – Health Insurance Portability and Accountability Act of 1996.

“HIX” – Health Insurance Exchange.

“IRS” – United States Internal Revenue Service.

“M&O” – Maintenance and Operations.

“MARS-E 2.0” – Minimal Acceptable Risk Security and Privacy Controls for Exchanges.

“NPN” – National Producer Number.

“OEP” – Open Enrollment Period.

“PERT” – Program Evaluation and Review Technique.

“PID” – Pennsylvania Insurance Department.

“PII” – Personally Identifying Information.

“PMBOK” – Project Management Body of Knowledge.

“QHP” – Qualified Health Plan.

“QLE” – Qualifying Life Event.

“Responsible” – As defined in Section 3.3 Offeror Responsibility.

“RFP” – Request for Proposals.

“SADP” – Stand-alone Dental Plan.

“SBE” – State-Based Exchange.

“SBE-FP” – State-Based Exchange using the Federal Platform.

“SEP” – Special Enrollment Period.

“SERFF” – System for Electronic Rates & Forms Filing.

“SHOP” – Small Business Health Options Program.

“SMS” – Short Message Service.

“SSAE” – Statement on Standards for Attestation Engagements.

“SWICA” – State Wage Information Collection Agency.

“Technology Platform” - The complete technology stack—including software, hardware, and infrastructure—anticipated to provide the ancillary health insurance Exchange functions detailed in Section 5, as well as the human resources required to develop, configure, implement and maintain that technology stack.

“Technical Submission” – The entire Offeror’s response to all aspects of this RFP (e.g. technical information, business operations information, functional information, etc.) with the exception of cost information which must all be provided in a separate electronic file(s).

“Technology Transition” – Technology Transition to operation as an SBE.

“TT” – Technology Transition to operation as an SBE.

“UAT” – User Acceptance Testing.

“WCAG” – Web Content Accessibility Guidelines.

When the Department uses “include” or “including,” it means “including but not limited to” or “include but not limited to.”

  - Purpose.

The Pennsylvania Health Insurance Exchange Authority (“Authority”), with the assistance of the Pennsylvania Insurance Department (“Department” or “PID”), is issuing this Request for Proposals (“RFP”) to provide those interested in submitting proposals (“Offerors”) sufficient information to enable them to prepare and submit proposals to provide and operate a technology platform and consumer assistance center for the Pennsylvania Health Insurance Exchange.  This RFP contains instructions governing the requested proposals, including the requirements for the information and material to be included; a description of the service to be provided; requirements which Offerors must meet to be eligible for consideration; general evaluation criteria; and other requirements specific to this RFP.

  - Issuing Office

The Authority with the assistance of the PID’s Bureau of Administration, (“Issuing Office”) has issued this RFP on behalf of the Commonwealth. The sole point of contact in the Commonwealth for this RFP shall be Mark Lapkowicz, mlapkowicz@pa.gov, the Issuing Officer for this RFP. Please refer all inquiries to the Issuing Officer.

  - Project Description

Pursuant to Act 42 of 2019, signed into law on July 2, 2019, the Commonwealth of Pennsylvania, through the Authority, is implementing a State-Based Exchange (“Exchange” or “SBE”) for plan year 2021, as contemplated by the Patient Protection and Affordable Care Act (“ACA”).  The Exchange is a technology solution and business operation marketplace in which individuals can shop for, compare and enroll in health insurance coverage.

The Authority, through the PID as the Issuing Office, is seeking a single qualified Offeror to provide, implement, operate and maintain an integrated technology-based health insurance exchange technology platform and associated consumer assistance center, including mailroom services to support the Authority’s anticipated operation as an SBE.   This request is being issued in anticipation of a transition to operation as an SBE effective November 2020, to provide enrollment in Qualified Health Plans (“QHP’s”) with coverage effective January 1, 2021.

The Authority intends to award a single contract to one Selected Offeror on a statewide basis pursuant to this RFP; however, Offerors may fulfill obligations under the contract by subcontracting with third parties.  The Offeror’s proposal shall identify the specific scope of services being offered, and which, if any, would be fulfilled by a subcontracted third party.   Any subcontracting will be managed by, and will be the sole responsibility of, the selected Offeror, and no subcontractor will have a direct relationship with the Authority.

The Project involves two components, both of which are related to services required for the operation of an SBE by the Authority:  (1) one component is for a proposed solution involving a comprehensive health insurance exchange technology platform that is currently in use by at least one other SBE and can be re-configured and re-deployed for use by the Authority in Pennsylvania; and (2) the second component is for a consumer assistance center to support the Authority’s operation as an SBE.  A high level of integration and interoperability between the consumer assistance center and the Exchange’s technology platform is required.

The Authority will administer the contract resulting from this RFP.  The resulting contract shall be for an initial term ending after SBE Plan Year 2024 (December 31, 2024), with the option to renew for five (5) additional single SBE plan years, if such renewals are in the best interest of the Authority and Commonwealth.

  - Objectives.

    - General.

Pursuant to Act 42 of 2019, the Commonwealth of Pennsylvania is transitioning from relying on the Federally-Facilitated Exchange (“FFE”) to a State-Based Exchange using the Federal Platform (“SBE-FP”) for plan year 2020, with a complete transition to an SBE for plan year 2021.  As an SBE-FP, eligibility and enrollment functions will be provided by the FFE, while marketing and outreach will be carried out by the Commonwealth. Once Pennsylvania transitions to an SBE, all of these functions will be carried out by the Authority and use of the SBE-FP will be discontinued; the services provided by the Selected Offeror will play a critical and integral role in that transition.

The Authority is seeking proposals to provide an Information Technology (IT) and business services solution, as outlined below and throughout this RFP, that will enable it to offer a net cost savings to Pennsylvania when compared to the costs of the user fee involved in an FFE, while also providing the tools to offer an improved user experience for Pennsylvania’s consumers, insurance carriers, producers, and non-profit partners.

The IT and business service solution (herein referred to as “solution” or “the solution”) sought through this RFP must:

- Rely on information system, information technology hosting services, and business process outsourcing services whose real-world operability and efficiency has been proven.

- Include systems that support the full breadth of health insurance exchange operations as outlined in this RFP: plan management, eligibility management, marketplace access and experience management including consumer shopping, comparison and selection of plans, enrollment management, financial management, broker and navigator supports, a broad range of customer service supports – hereafter referred as a consumer assistance center – which must include a call center, and mailroom services.

- Conform with all applicable state and federal laws and regulations governing information security and the protection of information privacy and confidentiality.

Proposals that involve reliance upon solutions whose real-world operability has not been proven are neither requested nor desired.  The proposal must include consumer assistance solutions (including call centers) for the SBE.  While the Exchange is ultimately seeking an integrated exchange platform and consumer assistance solution, contemplation of leveraging contracts with third-party subcontracted vendors to perform certain functions will be entertained, with an expectation that any such contemplation is accompanied by assurances of ultimate accountability by the Offeror, and demonstration that the third-party subcontracted vendor has successfully deployed such functionalities in existing SBEs.

For more information on the Exchange please visit www.insurance.pa.gov/SBEInfo, and for additional information on the requirements for the proposal, refer to Section 4 – Technical Submission.

    - Specific Goals and Objectives.

The Selected Offeror must ensure that the following goals and objectives of the Authority in the operation of the SBE are met:

- Reduce operational costs by transitioning away from reliance on the FFE and to autonomous operation as an SBE.  This reduction in operational costs is essential to the operation of the reinsurance program envisioned in Act 42 of 2019, and the savings must be significant enough to fund the state’s contribution to the operation of the reinsurance program in its entirety (see Act 42, §§ 9305(b)(4), 9503(b)(2)).

- Improve the quality of the user experience from the existing Exchange for consumers, partners, and staff; and increase the efficiency of the current Exchange’s operations through improved program integrity and business intelligence reporting.

- Transition to operation as an SBE effective November 2020, to provide enrollment in QHP’s and stand-alone dental plans (“SADP’s”) with effective coverage beginning January 1, 2021.

- Meet the federal requirements for the SBE, which may be found at ACA § 1311, codified at 42 U.S.C. § 18031, and the implementing regulations at 45 C.F.R. Subt. A, Subch. B Part 155, and any other any other applicable federal or state requirements relating to the SBE such as IRS Pub 1075, Safeguards for Protecting Federal Tax Returns and Return Information.

- Provide to the citizens of Pennsylvania a comprehensive, easy to use and simple to interact with health insurance exchange for individuals and small businesses throughout the entire insurance plan life cycle including but not limited to initial shopping, eligibility determination, plan selection, enrollment, billing, claims handling, and renewals, etc.

  - Capacity Background Information.

The following tables represent Pennsylvania’s application, plan selection, and enrollment metrics for Plan Year 2019 (source: CMS 2019 Marketplace Open Enrollment Period Public Use Files).

Plan Year 2019 Applications for QHP Coverage

| Number of Submitted Applications | Individuals Applying for Coverage on Submitted Applications | Individuals Determined Eligible to Enroll in an Exchange Plan | Individuals Determined Eligible to Enroll, with Financial Assistance | Individuals Determined or Assessed Eligible for Medical Assistance/ CHIP by the Exchange |
| --- | --- | --- | --- | --- |
| 332,268 | 475,070 | 415,480 | 331,982 | 59,631 |

Plan Year 2019 Plan Selections

| Total Number of Consumers Who Have Selected an Exchange Plan | New Consumers | Total Re-enrollees | Active Re-enrollees | Automatic Re-enrollees |
| --- | --- | --- | --- | --- |
| 365,888 | 66,490 | 299,398 | 201,349 | 98,049 |

In plan year 2019, Pennsylvania’s Medical Assistance Program received 124,957 consumer applications from the FFE and sent 341,465 consumer applications to the FFE. While enrollment volumes are included in the referenced table, processing of these consumer applications must be considered in the proposal.

  - Type of Contract.

It is proposed that if the Authority enters into a contract as a result of this RFP, it will be a Firm, Fixed Price Contract containing the Standard Contract Terms and Conditions attached hereto in Appendix E.  The Authority in its sole discretion, may undertake negotiations with Offerors whose proposals, in the judgment of the Authority, show them to be qualified, Responsible and capable of performing the Project.

- Proposal process & Requirements

  - Incurring Costs.

Neither the Authority nor Department is liable for any costs an Offeror incurs in preparation and submission of its proposal, in participating in the RFP process or in anticipation of award of the contract.

  - Pre-Proposal Conference.

The Authority will not hold a pre-proposal conference.  However, should any Offeror seek clarification of the RFP, Offerors may forward all questions to the Issuing Officer in accordance with Section 2.3 to ensure adequate time for analysis before the Authority provides an answer.  The Authority will post all questions and written answers on the same site as the original posting of this RFP as an addendum to, and as a part of, this RFP.

  - Questions & Answers.

If an Offeror has any questions regarding this RFP, the Offeror must submit the questions by email (with the subject line “RFP #6100048766 Question”) to the Issuing Officer named in Section 1.3 of the RFP. If the Offeror has questions, they must be submitted via email no later than the date indicated on the Calendar of Events. The Offeror must not attempt to contact the Issuing Officer by any other means. The Issuing Office will post all questions and written answers within this site by the date stated in the Calendar of Events. An Offeror who submits a question after the deadline date for receipt of questions indicated on the Calendar of Events assumes the risk that its proposal will not be responsive or competitive because the Authority is not able to respond before the proposal receipt date or in sufficient time for the Offeror to prepare a responsive or competitive proposal. When submitted after the deadline date for receipt of questions indicated on the Calendar of Events, the Issuing Officer may respond to questions of an administrative nature by directing the questioning Offeror to specific provisions in the RFP. To the extent that the Authority decides to respond to a non-administrative question after the deadline date for receipt of questions indicated on the Calendar of Events, the Authority will provide the answer to all Offerors through an addendum. All questions and responses as posted on the Department of General Services (“DGS”) website are considered as an addendum to, and part of, this RFP in accordance with Section 2.4. Each Offeror is responsible for monitoring the DGS website for new or revised RFP information. The Authority will not be bound by any verbal information, nor will it be bound by any written information that is not either contained within the RFP or formally issued as an addendum by the Issuing Office.

  - Addenda to the RFP.

If the Authority deems it necessary to revise any part of this RFP before the proposal response date, the Issuing Office will post an addendum within the site of original publication for this RFP.  It is the Offeror’s responsibility to check the website for any new information or addenda to the RFP. Answers to the questions asked during the Questions & Answers period also will be posted within this site as an addendum to the RFP.

  - Response Date.

To be considered for evaluation, proposals must arrive via email at the Issuing Office to Mark Lapkowicz at mlapkowicz@pa.gov before the time and date specified in the RFP Calendar of Events. The Authority will not accept proposals via facsimile transmission or any other form or format other than email containing files of the .PDF, .xlsx, or docs format.  Offerors should allow sufficient delivery time for the timely receipt of their proposals. Additionally, Offerors should allow sufficient time for the electronic uploading and transmission of documents via email. The Authority has the ability to reject, unopened, any late proposals.

  - Rejection of Proposals.

The Authority and the Department, assisting the Authority, in their sole and complete discretion, may reject any proposal received as a result of this RFP.

  - Proposal Submission.

To be considered, Offerors must submit a complete emailed electronic response to this RFP to the Issuing Office, using the format provided in Section 2.8 below in combination with Section 4 and Section 7 in their entirety, one or more files comprising the Technical Submittal and one or more files for the Cost Submittal.  All files are to be named as follows:

[RFP #6100048766] [Offeror Name] Technical Response File [# of file] of [Total # of files]

Or

[RFP #6100048766] [Offeror Name] Cost Response File [# of file] of [Total # of files]

Files should be sent in PDF format whenever possible.  Should any individual file size exceed 25MB it is recommended that the file(s) be split into separate files with each file containing one or more of the complete Tabs listed in Section 2.8.

The Offeror must make no other distribution of its proposal to any other Offeror or Commonwealth official or Commonwealth consultant. An official authorized to bind the Offeror to its provisions must sign the proposal. If the official signs the Proposal Cover Sheet (Attachment A to this RFP) and the Proposal Cover Sheet is attached to the Offeror’s proposal, the requirement will be met. For this RFP, the proposal must remain valid for one hundred and twenty (120) calendar days or until a contract is fully executed. If the Authority selects the Offeror’s proposal for award, the contents of the selected Offeror’s proposal will become, except to the extent the contents are changed through Best and Final Offers (“BAFO”) or negotiations, contractual obligations. Each Offeror submitting a proposal specifically waives any right to withdraw or modify it, except that the Offeror may withdraw its proposal by written notice received at the Issuing Office address for proposal delivery prior to the exact hour and date specified for proposal receipt. An Offeror or its authorized representative may withdraw its proposal in person prior to the exact hour and date set for proposal receipt, provided the withdrawing person provides appropriate identification and signs a receipt for the proposal. An Offeror may modify its submitted proposal prior to the exact hour and date set for proposal receipt only by submitting a new sealed proposal or sealed modification marked as “Revised Proposal” which complies with the RFP requirements.

  - Proposal Format.

Offerors must submit their proposals in the format, using the Tab and Section headings, shown in Section 2.8. All files must be prepared in “print ready” format to be printed in US Letter, US Legal or US Tabloid sizes only with right and left margins of one (1) inch and be double-sided.  Proposals must use Arial or Times New Roman font with a size of 12pt.  Excel documents must be formatted for printing with font sizes of no less than 12pt.

Each page of the proposal must include a page number and identification of the Offeror in the page footer.  Materials provided in any appendix must be specifically referenced by page numbers in the body of the proposal.

To be considered, the proposal must respond to all proposal requirements. Offerors should provide any other information thought to be relevant, but not applicable to the enumerated categories, as an appendix to the proposal. All cost data relating to this proposal must be in a file separate from the Technical Submission.  The Technical Submission must not include any cost information whatsoever either directly or in such form where the costs can be derived solely from information within the Technical Submission. Offerors should not reiterate technical information in the cost submittal. Each proposal must consist of at least two separate files as follows:

    - Technical Submittal:

In response to Part III, the Technical Submittal must include a signed Transmittal Letter (or signed Proposal Cover Sheet found in Attachment A of this RFP) and include Tabs 1 through 15. Offerors must format their responses as follows:

- Tab 1: Table of Contents

- Tab 2:

  - Summary of Proposed Solution (Section 4.1)

  - Understanding of the Project (Section 4.2)

- Tab 3:

  - Company Overview (Section 4.3)

  - Prime Contractor Responsibilities (Section 4.4)

- Tab 4: Prior Experience (Section 4.5)

- Tab 5: Personnel (Section 4.6)

- Tab 6: Subcontracting Plan (Section 4.7)

- Tab 7: Financial Capability (Section 4.8)

- Tab 8: Delivering and Achieving All Functional and Technical Requirements (Section 4.9)

- Tab 9: Service Levels and Associated Penalties (Section 4.10)

- Tab 10:  Testing Approach (Section 4.11)

- Tab 11:  Roles and Responsibilities (Section 4.12)

- Tab 12:  Timeline and Deliverables (Section 4.13)

- Tab 13:

  - Required Non-Services Items (Section 4.14)

  - Considerations for Changes (Section 4.15)

  - General Constraints (Section 4.16)

- Tab 14: Emergency Preparedness (Section 4.17)

- Tab 15: Mandatory Submissions to be completed and signed

  - Proposal Cover Sheet (Attachment A)

  - Business Associate Agreement (Attachment C)

  - Cloud Use Case Questionnaire (Attachment E)

  - Iran Free Certification Form (Attachment G)

When submitting these documents, should the combined document, in PDF format, be larger than 25MB then Offerors are encouraged to break the files into sub-files organized by Tab number.

    - Cost Submittal in compliance with Section 7 of this RFP

The Authority may request additional information that, in the Authority’s opinion, is necessary to ensure that the Offeror’s competence, number of qualified employees, business organization, and financial resources are adequate to perform according to the RFP. The Authority may make investigations as deemed necessary to determine the ability of the Offeror to perform, and the Offeror must furnish to the Authority and the Department all requested information and data. The Authority may reject any proposal if the evidence submitted by, or investigation of, such Offeror fails to satisfy the Authority that such Offeror is properly qualified to carry out the obligations of the RFP and to complete the project as specified.

The Technical Submission requirements of the RFP involve two components, both of which are related to services required for the operation of an SBE by the Authority.  Offerors must submit proposals which address both parts of the Technical Submission: (1) one component is for a proposed solution involving a health insurance exchange technology platform that is currently in use by at least one other SBE and can be re-configured and re-deployed for use by the Authority in Pennsylvania; and (2) the second component is for a consumer assistance center to support the Authority’s operation as an SBE. Mailroom services are also required to support these components.  A high level of integration and interoperability between the consumer service center and the Exchange’s technology platform is required.

  - Economy of Preparation.

Offerors should prepare proposals simply and economically, providing a straightforward, concise description of the Offeror’s ability to meet the requirements of the RFP.

  - Alternate Proposals.

The Authority has identified the basic approach to meeting its requirements for this project, allowing Offerors to be creative and propose their best solution to meeting these requirements. The Authority will not accept alternate proposals.

  - Discussions for Clarification.

Offerors may be required to make an oral or written clarification of their proposals to the Issuing Office to ensure thorough mutual understanding and Offeror responsiveness to the solicitation requirements. The Issuing Office will initiate requests for clarification. Clarifications may occur at any stage of the evaluation and selection process prior to contract execution.

  - Proposal Contents.

    - Confidential Information.

The Commonwealth is not requesting, and does not require, confidential proprietary information or trade secrets to be included as part of Offerors’ submissions in order to evaluate proposals submitted in response to this RFP. Accordingly, except as provided herein, Offerors should not label proposal submissions as confidential or proprietary or trade secret protected. Any Offeror who determines that it must divulge such information as part of its proposal must submit the signed written statement described in Subsection 2.12.3 below and must additionally provide a redacted version of its proposal, which removes only the confidential proprietary information and trade secrets, for required public disclosure purposes.

    - Commonwealth Use.

All material submitted with the proposal will be considered the property of the Commonwealth and may be returned only at the Authority’s option. The Commonwealth has the right to use any or all ideas not protected by intellectual property rights that are presented in any proposal regardless of whether the proposal becomes part of a contract. Notwithstanding any Offeror copyright designations contained on proposals, the Commonwealth will have the right to make copies and distribute proposals internally and to comply with public record or other disclosure requirements under the provisions of any Commonwealth or United States statute or regulation, or rule or order of any court of competent jurisdiction.

    - Public Disclosure.

After the award of a contract pursuant to this RFP, all proposal submissions are subject to disclosure in response to a request for public records made under the Pennsylvania Right-to-Know-Law, 65 P.S. § 67.101, et seq. If a proposal submission contains confidential proprietary information or trade secrets, a signed written statement to this effect must be provided with the submission in accordance with 65 P.S. § 67.707(b) for the information to be considered exempt under 65 P.S. § 67.708(b)(11) from public records requests. Refer to the Appendix A for a Trade Secret Confidential Proprietary Information Notice Form that may be utilized as the signed written statement, if applicable. Financial capability information that is submitted in response to Section 4.8 of this RFP, such financial capability information is exempt from public records disclosure under 65 P.S. § 67.708(b) (26).

  - Presentations.

The Authority reserves the right to hold presentations and live demonstrations with any qualified Offerors.

  - Objections and Additions to Standard Contract Terms and Conditions.

The Authority will not entertain any objections to the terms and conditions contained in Appendix E.  The Issuing Office will reject any proposal that is conditioned on the negotiation of the terms and conditions set out in the Terms and Conditions contained in Appendix E or to other provisions of the RFP.

  - Best and Final Offers (“BAFO”).

    - BAFO Discussions.

While not required, the Authority may conduct discussions with Offerors for the purpose of obtaining BAFO’s. To obtain BAFO’s from Offerors, the Authority may do one or more of the following, in any combination and order:

1. Schedule oral presentations and system demonstrations;

2. Request revised proposals;

3. Conduct a reverse online auction; and

4. Enter into pre-selection negotiations.

    - Excluded Offerors.

The following Offerors will not be invited by the Authority to submit a BAFO:

- Those Offerors that the Authority has determined to be not Responsible or whose proposals the Authority has determined to be not responsive.

- Those Offerors that the Authority has determined in accordance with Section 3.3 from the submitted and gathered financial and other information, do not possess the financial capability, experience or qualifications to ensure good faith performance of the contract.

- Those Offerors whose score for their technical submittal of the proposal is less than 75% of the total amount of raw technical points allotted to the technical criterion.

The Authority may further limit participation in the BAFO process to those remaining Responsible Offerors, which the Authority has, within its discretion, determined to be within the top competitive range of responsive proposals.

    - BAFO Evaluation Criteria.

The Evaluation Criteria found in Section 3.5, shall also be used to evaluate the BAFOs, as applicable.

    - Price Reductions.

Price reductions offered through a BAFO process must have no effect upon the scope of the Offeror’s Technical Submittal.

  - News Releases.

Offerors must not issue news releases, Internet postings, advertisements or any other public communications pertaining to this project without prior written approval of the Authority, and then only in coordination with the Authority.

  - Restriction of Contact.

From the issue date of this RFP until the Authority selects a proposal for award, the Issuing Officer is the sole point of contact concerning this RFP. Any violation of this condition may be cause for the Authority to reject the offending Offeror’s proposal. If the Authority later discovers that the Offeror has engaged in any violations of this condition, the Authority may reject the offending Offeror’s proposal or rescind its contract award. Offerors must agree not to distribute any part of their proposals beyond the Issuing Office. An Offeror who shares information contained in its proposal with other Commonwealth personnel and/or competing Offeror personnel may be disqualified.

  - Authority Participation.

Offerors must provide all services, supplies, facilities, and other support necessary to complete the identified work, except as otherwise provided in this Section 2.16.  The Authority will assign a staff member as the project and contract administrator to serve as the single point of contact for the Selected Offeror.  That staff member shall be responsible for: (1) initial coordination of communications between Selected Offeror and the Authority’s external stakeholders, including points of contact and communications protocols; (2) review, management, and approval of the project plans and control structures developed by the Selected Offeror; and (3) approval of any deliverables required by this RFP.

The Authority’s project and contract manager shall also administer and monitor the contract resulting from this RFP. The Authority and PID will provide necessary business and technical subject matter experts. The Authority will provide the following items regardless of physical location: (1) access to required Commonwealth site facilities; (2) access to project facilities; and (3) access to required project documentation.

Neither the Authority nor PID will provide administrative or clerical support staff to the selected Offeror.

  - Term of Contract.

The term of the contract will be from the date of contract execution through SBE Plan Year 2024 (December 31, 2024), with the option to renew the contract for five additional SBE plan years.  The contract will begin on the Effective Date, which will be the date of final execution of a Contract between the Authority and the Selected Offeror and all approvals required by Commonwealth contracting procedures have been obtained.  The Selected Offeror must not start the performance of any work prior to the Effective Date of the contract and the issuance of a Notice to Proceed or Purchase Order.  The Authority will not be liable to pay the Selected Offeror for any service or work performed or expenses incurred before the Effective Date of the contract.

  - Offeror’s Representations and Authorizations.

By submitting its proposal, each Offeror understands, represents, and acknowledges that:

    - All of the Offeror’s information and representations in the proposal are material and important, and the Authority will rely upon the contents of the proposal in awarding the contract. The Commonwealth may treat any misstatement, omission or misrepresentation as fraudulent concealment of the true facts relating to the Proposal submission, punishable pursuant to 18 Pa. C.S. § 4904.

    - The Offeror has arrived at the price(s) and amounts in its proposal independently and without consultation, communication, or agreement with any other Offeror or potential Offeror.

    - The Offeror has not disclosed the price(s), the amount of the proposal, nor the approximate price(s) or amount(s) of its proposal to any other firm or person who is an Offeror or potential Offeror for this RFP, and the Offeror must not disclose any of these items on or before the proposal submission deadline specified in the Calendar of Events of this RFP.

    - The Offeror has not attempted, nor will it attempt, to induce any firm or person to refrain from submitting a proposal on this contract, or to submit a proposal higher than this proposal, or to submit any intentionally high or noncompetitive proposal or other form of complementary proposal.

    - The Offeror makes its proposal in good faith and not pursuant to any agreement or discussion with, or inducement from, any firm or person to submit a complementary or other noncompetitive proposal.

    - To the best knowledge of the person signing the proposal for the Offeror, the Offeror, its affiliates, subsidiaries, officers, directors, and employees are not currently under investigation by any governmental agency and have not in the last four (4) years been convicted or found liable for any act prohibited by State or Federal law in any jurisdiction, involving conspiracy or collusion with respect to bidding or proposing on any public contract, except as the Offeror has disclosed in its proposal.

    - To the best of the knowledge of the person signing the proposal for the Offeror and except as the Offeror has otherwise disclosed in its proposal, the Offeror has no outstanding, delinquent obligations to the Commonwealth including, any state tax liability not being contested on appeal or other obligation of the Offeror that is owed to the Commonwealth.

    - The Offeror is not currently under suspension, debarment, or precluded from participation in any federally funded healthcare program by the Commonwealth, any other state or the federal government, and if the Offeror cannot so certify, then it must submit along with its proposal a written explanation of why it cannot make such certification.

    - The Offeror has not made, under separate contract with the Department, any recommendations to the Department concerning the need for the services described in its proposal or the specifications for the services described in the proposal.

    - Each Offeror, by submitting its proposal, authorizes Commonwealth agencies to release to the Commonwealth information concerning the Offeror's Pennsylvania taxes, unemployment compensation and workers’ compensation liabilities.

    - Until the selected Offeror receives either an emergency purchase order or a fully executed and approved written contract from the Issuing Office, there is no legal and valid contract, in law or in equity, and the Offeror must not begin to perform.

    - The Offeror is not currently engaged and, will not during the duration of the contract engage, in a boycott of a person or an entity based in or doing business with a jurisdiction which the Commonwealth is not prohibited by Congressional statute from engaging in trade or commerce.

  - Notification of Selection.

    - Contract Negotiations.

The Authority or PID will notify all Offerors in writing of the Offeror selected for contract negotiations after the Authority has determined, taking into consideration all the evaluation factors, the proposal that is the most advantageous to the Authority.

    - Contract Award.

Offerors whose proposals are not selected will be notified when contract negotiations have been successfully completed and the Authority has received the final negotiated contract signed by the selected Offeror.

  - Debriefing Conferences.

Upon notification of award, Offerors whose proposals were not selected will be given the opportunity to be debriefed. The Authority or PID will schedule the debriefing at a mutually agreeable time. The debriefing will not compare the Offeror with other Offerors, other than the position of the Offeror’s proposal in relation to all other Offeror proposals. An Offeror’s exercise of the opportunity to be debriefed does not constitute nor toll the time for filing a protest (see Section 2.21).

  - RFP Protest Procedure.

Offerors and prospective Offerors who are aggrieved in connection with the solicitation or award of the contracts under this RFP may file a protest with the Authority. Any such protest must be in writing and must comply with the requirements set forth in the Commonwealth Procurement Code at 62 Pa.C.S. §1711.1. Any protest filed in relation to this RFP must be delivered to:

Pennsylvania Health Insurance Exchange Authority

c/o Pennsylvania Insurance Department

Bureau of Administration

1327 Strawberry Square

Harrisburg, Pennsylvania 17120

Offerors and prospective Offerors should file a protest electronically via email to the Issuing Officer’s email account (mlapkowicz@pa.gov) , but also must simultaneously send the original and two (2) hard copy versions of the protest to the address listed above.

  - Use of Electronic Versions of this RFP.

This RFP is being made available by electronic means. If an Offeror electronically accepts the RFP, the Offeror acknowledges and accepts full responsibility to ensure that no changes are made to the RFP. In the event of a conflict between a version of the RFP in the Offeror’s possession and the Issuing Office’s version of the RFP, the Issuing Office’s version shall govern.

- CRITERIA FOR SELECTION

  - Mandatory Responsiveness Requirements.

To be eligible for selection, a proposal must:

- Be timely received from an Offeror (see Section 2.5); and

- Be properly signed by the Offeror (see Section 2.7).

  - Technical Nonconforming Proposals.

The two (2) Mandatory Responsiveness Requirements set forth in Section 3.1 above are the only RFP requirements that the Commonwealth will consider to be non-waivable. The Authority may, in its sole discretion: (1) waive any other technical or immaterial nonconformities in an Offeror’s proposal, (2) allow the Offeror to cure the nonconformity, or (3) consider the nonconformity in the scoring of the Offeror’s proposal.

  - Offeror Responsibility.

To be Responsible, an Offeror must submit a responsive proposal and possess the capability to fully perform the contract requirements in all respects and the integrity and reliability to ensure good faith performance of the contract. In order for an Offeror to be considered Responsible for this RFP and, therefore, eligible for selection for BAFO’s or selection for contract negotiations:

A. The total score for the technical submittal of the Offeror’s proposal must be greater than or equal to seventy five percent (75%) of the available raw technical points; and

B. The Offeror’s financial information must demonstrate that the Offeror possesses the financial capability to ensure good faith performance of the contract.

The Commonwealth will review the Offeror’s previous three (3) annual financial statements, any additional information received from the Offeror, and any other publicly-available financial information concerning the Offeror and assess each Offeror’s financial capacity based on calculating and analyzing various financial ratios, and comparison with industry standards and trends. An Offeror which fails to demonstrate sufficient financial capability to ensure good faith performance of the contract as specified may be considered by the Authority, in its sole discretion, for BAFO or contract negotiation contingent upon such Offeror providing contract performance security for the first contract year cost proposed by the Offeror in a form acceptable to the Authority. Based on the financial condition of the Offeror, the Authority may require a certified or bank (cashier’s) check, letter of credit, or a performance bond conditioned upon the faithful performance of the contract by the Offeror. The required performance security must be issued or executed by a bank or surety company authorized to do business in the Commonwealth. The cost of the required performance security will be the sole responsibility of the Offeror and may not increase the Offeror’s cost proposal or the contract cost to the Commonwealth. Further, the Authority will award a contract only to an Offeror determined to be responsible in accordance with the most current version of Commonwealth Management Directive 215.9, Contractor Responsibility Program.

  - Evaluation.

The Authority has selected a committee of qualified personnel to review and evaluate timely submitted proposals. The Authority will notify in writing of its selection for negotiation the Responsible Offeror whose proposal is determined to be the most advantageous to the Commonwealth as determined by the Authority after taking into consideration all of the evaluation factors.

  - Evaluation Criteria.

The following criteria will be used in evaluating each proposal:

    - Technical.

The Department has established the weight for the Technical criterion for this RFP as ninety percent (90%) of the total points. Evaluation will be based upon the following criteria:

- Soundness of solution and approach

- Excellence of customer experience and overall solution usability

- Offeror and personnel qualifications

- Understanding the problem

- Ability to meet solution requirements both functional and technical

- Soundness of approach to implementation, maintenance and operations

- Offeror qualifications including relevant experience, capacity to implement, maintain and operate

- References

- Field-proven solution

- Comprehensive solution

- Ability to meet timelines

- Operations and solution that meets or exceeds industry best-practices services, technology, operations and quality.

Proposals involving solutions whose real-world operability has not been proven may be rejected without complete evaluation by the Evaluation Committee.

The final Technical scores are determined by giving the maximum number of technical points available to the proposal with the highest raw technical score. The remaining proposals are rated by applying the Technical Scoring Formula set forth at the following webpage: https://www.dgs.pa.gov/Materials-Services-Procurement/Procurement-Resources/Pages/RFP_SCORING_FORMULA.aspx

    - Cost.

The Department has established the weight for the Cost criterion for this RFP as ten percent (10%) of the total points. The cost criterion is rated by giving the proposal with the lowest total cost the maximum number of Cost points available. The remaining proposals are rated by applying the Cost Formula set forth at the following webpage: https://www.dgs.pa.gov/Materials-Services-Procurement/Procurement-Resources/Pages/RFP_SCORING_FORMULA.aspx.  Note that the requirements for Small Diverse Business, Small Business and Domestic Workforce Utilization do not apply to this procurement.

  - Final Ranking and Award.

    - After any BAFO process is conducted, the Authority will combine the evaluation committee’s final technical scores and the final cost scores, in accordance with the relative weights assigned to these areas as set forth in this Part.

    - The Authority will rank Responsible Offerors according to the total overall score assigned to each, in descending order.

    - Except as provided in this Section 3.6 the Authority must select for contract negotiations the Offeror with the highest overall score.

    - The Authority has the discretion to reject all proposals or cancel the request for proposals, at any time prior to the time a contract is fully executed, when it is in the best interests of the Authority. The reasons for the rejection or cancellation shall be made part of the contract file.

- TECHNICAL SUBMITTAL – Response format

When preparing the Technical Submission, the following guidelines, templates and structure shall be followed.  The Commonwealth invites Offerors to provide as much information as possible to clearly communicate to the Evaluation Committee all aspects of the offering. However, the Commonwealth is only seeking information that would enable the Evaluation Committee to make a very well-informed decision.  Therefore, general marketing materials from the Offeror are not requested or desired as part of the proposal.  Offerors should be efficient and succinct in their proposals relative to the information required by the section of the RFP or where the Offeror believes that such information will be essential to the Evaluation Committee making a well-informed decision.

  - Summary of Proposed Solution

Offerors must provide a description of their proposed solution, not to exceed three pages including diagrams, where they clearly outline:

- The various components of the solution,

- Which entity (including subcontractors) is the supplier of each component,

- How the Offeror will ensure that the various components will be interfaced to external systems (including to FDSH, DHS, insurance carriers) and managed to function as an integrated IT and business services solution for Pennsylvania’s SBE, and

- A value proposition statement, not to exceed half a page, in which the Offeror identifies the features of its proposed solution that, in the Offeror’s estimation, sets it apart from competitors.

  - Understanding of the Project.

Offerors must state in the technical submittal in succinct terms their understanding of the project presented and the services required by this RFP.

  - Qualifications.

    - Company Overview.

In order to qualify to submit a proposal for this RFP, the Offeror must have demonstrated success in the development, implementation and maintenance of the technical platform for an SBE in another state, as well as demonstrated success in the development, implementation and maintenance of a consumer service center with functionality and requirements similar to those sought in this RFP.  Failure to meet these requirements could result in rejection of a proposal.  Offerors are permitted to partner with a subcontractor or subcontractors to meet these qualifications, but a single Offeror must be responsible for oversight, direction and management of both the technical platform and consumer service center aspects of the proposal and provide specific evidence that they meet these qualifications.

Offerors shall provide a company profile and overview that includes the following information:

- Company name and type of ownership (sole proprietor, partnership, corporation, etc.).

- State and date of incorporation.

- Number of years in business.

- List of top officers.

- Location of company headquarters, and the location of the office that will be responsible for the provision of services required by this RFP.

- Number of employees locally and nationally that have the expertise necessary to provide the services required by this RFP.

- Statement of whether the Offeror has ever been engaged under contract by any Commonwealth Pennsylvania agency, and if so, provide the name of the agency, a contact name, the dates and description of services provided, and the total value of the contract.

- Disclosure of any significant prior or ongoing contract failures, contract breaches, civil or criminal litigation in which the Offeror has been alleged to be liable or held liable in a matter involving a contract with the Commonwealth of Pennsylvania, any other governmental entity, or any private entity.

- Disclosure of any pending claim or litigation occurring within the past six (6) years that may adversely affect the Offeror’s ability to perform or fulfill its obligations if a contract is awarded as a result of this RFP, including the date and description of the alleged contract failure or breach, the parties involved, the status of the claim or litigation, the amount in controversy, and the court and docket number (if applicable).

- A brief company background/history and statement of why the Offeror is qualified to provide the services described in this RFP.

- A brief description of the length of time Offeror has been providing services described in this RFP to the public and/or private sector.

  - Prime Contractor Responsibilities.

The Selected Offeror must directly perform services valued at least at 50% of the total contract value. Nevertheless, the contract will require the Selected Offeror to assume responsibility for all services offered in its proposal whether it produces them itself or by subcontract. Further, the Authority will consider the Selected Offeror to be the sole point of contact with regard to all contractual matters.

  - Prior Experience.

Proposals should clearly indicate which capabilities of the proposed solution currently exist in their entirety, which would need to be developed or otherwise changed from currently developed capabilities for other SBE’s in operation, and which would be reliant on third party subcontracted vendors.  For components of the solution that need to be developed or changed, proposals should include detailed plans for successful development and implementation

Proposals should also clearly outline whether capabilities anticipated to be provided by a third-party subcontracted vendor exist in their entirety or would need to be developed or otherwise changed from currently developed capabilities by that third-party subcontracted vendor.

- The Authority will consider solutions that incorporate leveraging contracts with third-party subcontracted vendors to perform certain functions, with an expectation that any such proposal is accompanied by assurances of ultimate accountability by the Offeror, and demonstration that the third-party subcontracted vendors have successfully deployed such functionalities in existing SBEs.  The proposal must address how it will minimize the risk of disruption to the health insurers dedicated to serving Pennsylvania’s individual and small group markets, and the over 350,000 enrollees who secure critical coverage for health care through the plans sold on the Exchange.  The proposed solution shall minimize the resources required on behalf of the health insurers to enable a smooth transition.

- The Proposal should also address how the preferred solution will minimize the risk of disruption to Pennsylvania’s Medicaid administering agency, the Department of Human Services, which currently serves over 2.3 million Medical Assistance and Children’s Health Insurance Program (“CHIP”) recipients. The ideal health insurance exchange platform will provide dedicated user authentication and eligibility functionality independent from the DHS system, and will interface with the DHS system in precisely the same manner as the current configuration with the FFE.  However, it should also be capable of sharing integrated user authentication and/or eligibility functionality in the future without requiring a fundamental change to the platform’s architecture.  Appendix D provides a complete listing of all Commonwealth and external required interfaces and systems with which the solution must integrate at initial implementation.  Other interfaces and integration may be required in the future and will be accomplished via a change management process.

Technical Submissions must include a description of prior experience in providing a technical platform for the operation of an SBE and a consumer service center, especially with regard to the Offeror’s prior experience supporting each of the functions listed in Sections 5 and 6.

- Using the following table, indicate which exchanges have been supported by the technical platform in the Offeror’s proposal (provide the two-letter state abbreviation, and if applicable, the Exchange agency name); which plan years received support; and which, if any, of the functions listed in Sections 5.2 and 6 were NOT supported for each agency/plan year (the list of unsupported functions should be separated with semicolons). Use separate rows for each agency/plan year. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Exchange Functions NOT Supported |
| --- | --- | --- | --- |

Using the following table, indicate which, if any, of the supported functions were provided to the SBE(s) in part or in full by subcontractors. Provide the exchange agency name, the plan year, the number of the Exchange function (as listed in Sections 5.2 and 6), and the name of the subcontractor. Use separate rows for each agency/plan year/function. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Exchange Function | Subcontractor |
| --- | --- | --- | --- | --- |

Using the following table, indicate which, if any, of the Exchange functions listed in Sections 5.2 and 6 would NOT be supported or are partially supported by the proposed solution. Provide the number of the Exchange function (as listed in Sections 5.2 and 6) and an explanation detailing the circumstances of the omission. Use separate rows for each function. Add additional rows as necessary.

| Exchange Function | Explanation |
| --- | --- |

- The Authority requires that Offerors have experience providing each of the Customer Assistance functions listed in Section 5.3 and 6. Using the following table, indicate which exchanges have been supported by the proposed solution (provide the two-letter state abbreviation, if applicable, and the Exchange agency name); which plan years received support; and which, if any, of the functions listed in Sections 5.3 and 6 were NOT or were partially supported for each plan year (the list of functions should be separated with semicolons). Use separate rows for each agency/plan year. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Consumer Assistance Functions NOT Supported |
| --- | --- | --- | --- |

Using the following table, indicate which, if any, of the supported functions identified in Section 5.3 were provided to the exchange(s) in part or in full by subcontractors. Provide the agency name, the plan year, the number of the exchange function (as listed in 5.3), and the name of the subcontractor. Use separate rows for each agency/plan year/function. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Consumer Assistance Function | Sub-Contractor |
| --- | --- | --- | --- | --- |

Using the following table, indicate which, if any, of the consumer assistance functions listed in Section 5.3 would NOT be supported by the proposed solution. Provide the number of the Exchange function (as listed in Section 5.3) and an explanation detailing the circumstances of the omission. Use separate rows for each function. Add additional rows as necessary.

| Exchange Function | Explanation |
| --- | --- |

- The Authority requires that Offerors have experience providing each of the Mail Operations functions listed in Section 5.4 and 6. Using the following table, indicate which exchanges have been supported by the proposed solution (provide the two-letter state abbreviation, if applicable, and the Exchange agency name); which plan years received support; and which, if any, of the functions listed in Sections 5.4 and 6 were NOT or were partially supported for each plan year (the list of functions should be separated with semicolons). Use separate rows for each agency/plan year. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Consumer Assistance Functions NOT Supported |
| --- | --- | --- | --- |

Using the following table, indicate which, if any, of the supported functions identified in Section 5.4 were provided to the exchange(s) in part or in full by subcontractors. Provide the agency name, the plan year, the number of the exchange function (as listed in 5.4), and the name of the subcontractor. Use separate rows for each agency/plan year/function. Add additional rows as necessary.

| State | Exchange Agency Name | Plan Year | Consumer Assistance Function | Sub-Contractor |
| --- | --- | --- | --- | --- |

Using the following table, indicate which, if any, of the consumer assistance functions listed in Section 5.4 would NOT be supported by the proposed solution. Provide the number of the Exchange function (as listed in Section 5.4) and an explanation detailing the circumstances of the omission. Use separate rows for each function. Add additional rows as necessary.

| Exchange Function | Explanation |
| --- | --- |

  - Personnel.

The Authority seeks a highly capable, dedicated team from the Offeror that will work closely with the wide range of constituents involved in the SBE in Pennsylvania.  Due to the aggressive timelines and the Authority’s requirement to deploy an already-built solution that can be easily and quickly configured to the Authority’s needs, having personnel that have significant experience with SBEs and the Offeror’s product and will be dedicated to the Authority’s project is seen as a key to success.  To that end, Offerors are to provide a narrative that explains the staffing strategy and leverage of the Offeror’s best resources to achieve the Authority’s goals.

Additionally, Offerors are to describe in narrative and tabular form the total number of executive, professional, development, and any other personnel who will be engaged in the work. For each person indicate the following:

- Person’s first and last name (required for any Key Personnel, for non-key personnel for which the Offeror is not prepared to commit to their participation to this initiative at this time note “TBD”).

- Person’s corporate title (e.g. the title they would be billed at)

- A brief description of the role the person would be filling

- The primary location the person would be working from while engaged in the work (Country for non-US, City and State for U.S.)

- Provide detailed information for Key Personnel, which at a minimum is considered any person responsible for oversight, management of the services to be provided pursuant to this RFP and any lead personnel providing technical and substantive services relative to the SBE platform and consumer assistance center.  At a minimum, the Offeror’s Project Manager, Functional Lead(s), Technical Lead(s), Testing Lead(s), and Change Management Lead(s) are all considered to be Key Personnel.  For each of the Key Personnel, the Offeror’s response must include the employee’s name, and through a resume or similar document, the project personnel’s education and experience in the services requested by the Authority.  Indicate the responsibilities each individual will have in this project and how long each has been with your company.  For each Key Person, the Offeror should also indicate the person’s home State/City if they will be maintaining that residence during their term as a Key Personnel.

- Provide a detailed acknowledgment and plan to address the fact that the Authority has a preference for, to the maximum extent feasible, a dedicated Harrisburg, PA based team for the Offeror and any and all Offeror’s sub-contractors.  However, at a minimum it is expected that all Key Personnel will be located in the greater Harrisburg area (within 30 miles of the Authority’s offices) throughout the contract duration during normal working days/hours and easily accessible for in-person meetings with the Authority or their representatives, agency and industry partners.  Additionally, during critical times such as, but not limited to, deployments, addressing critical issues, system outages, or other high-priority, time-critical issues Key Personnel and other team-members are required to be located in the Harrisburg, PA area for the duration of such events and activities.

- For any Key Personnel, the Selected Offeror may not remove or replace the Key Person without agreement from the Authority and such agreement must be proceeded with a detailed transition plan, and an opportunity for the Authority staff to interview the proposed replacement.  Should a Key Person need to be replaced due to situations outside of the Selected Offeror’s control (such as but not limited to: resignation, termination, family or personal emergency, etc.), Offeror shall give the Authority immediate notice and within 10 business days provide proposed replacements and a proposed transition plan.

NOTE:  Should the Offeror be eligible to participate in presentations as indicated in the Calendar of Events and as defined in Section 2.23, all Key Personnel proposed are considered mandatory to attend the presentations in person.

  - Subcontractors:

Provide a subcontracting plan for all subcontractors who will be assigned to the project.  The Selected Offeror is prohibited from subcontracting or outsourcing any part of this project without the express written approval from the Commonwealth.  Upon award of the contract resulting from this RFP, subcontractors included in the proposal submission are deemed approved unless otherwise objected to by the Authority. For each position or service included in your subcontracting plan provide:

- Name of subcontractor;

- Primary contact name and email;

- Address of subcontractor;

- Description of services to be performed;

- Number of employees by job category assigned to this project; and

- Resumes (if appropriate and available);

- Description of how the work of any subcontractor(s) shall be supervised, channels of communication shall be maintained and compliance with contract terms assured; and

- The Offeror’s prior experience with the subcontractor.

  - Financial Capability.

Describe your company’s financial stability and economic capability to perform the contract requirements.  The Commonwealth reserves the right to request additional information to evaluate an Offeror’s financial capability.

  - Delivering and Achieving All Functional and Technical Requirements

Describe in detail the proposed solution’s ability to provide all the technical, functional and business operations functions detailed in Section 5.  The proposal must recognize that the proposed solution shall be required to comply with all federal requirements related to the establishment and operation of an SBE under the ACA, including but not limited to those requirements detailed in 45 C.F.R. Subt. A, Subch. B Part 155, and be capable of servicing at least a 20% increase in participant capacity and at least 100% in technical capacity and performance (e.g. size of database, number of accounts, number of transactions, etc. that can be handled by the system) versus the figures presented in Section 1.6 of this RFP.

Describe in narrative form your technical plan for delivering and achieving a solution that meets or exceeds the requirements set forth in Section 5 within the timelines and approach stated in this RFP and detailed in Section 6.  In providing a response use the task descriptions set forth in Section 6 as your reference point.  Modifications of the task descriptions are permitted; however, reasons for changes should be fully explained.  Indicate the number of person hours allocated to each task.  Include a Gantt chart or Program Evaluation and Review Technique (PERT) or similar type display, time related, showing each event.  If more than one approach is apparent, comment on why you chose this approach.

For mailroom requirements and Tasks, describe in narrative form your technical plan for accomplishing the work using the task descriptions set forth in Section 6.  Modifications of the task descriptions are permitted; however, reasons for changes should be fully explained.  Indicate the number of person hours allocated to each task.  Include a PERT or similar type display, time related, showing each event.  If more than one approach is apparent, comment on why you chose this approach.

  - Service Levels and Liquidated Damages

- Attachment F contains implementation, maintenance, operations and customer service levels that the Authority is proposing.  Offerors are to respond to these by stating if they agree to the service level and associated liquidated damages as proposed.  Where the Offeror does not agree with the measure, the quantification of the measure and/or the associated penalty for non-conformance, the Offeror is to propose alternative measures, quantifications or penalties that achieves the same or better intent and must also provide an explanation for the proposed change.  However, the Authority is under no obligation to accept any proposed changes, but will consider those proposed changes during the contract negotiation process.

- Additionally, describe any and all benchmarks and performance indicators (including target levels) implemented by the proposed solution to ensure a consistent level of performance throughout a plan year for the technical solution, the business operations, the Customer Assistance centers, and mailroom operations.

- Describe in detail if the Offeror has ever been assessed penalties, liquidated damages or has been subject of a contract termination or any legal action (even if the action resulted in a settlement or the customer dropped the action) with a U.S. state in the performance of a contract substantially similar to the solution as envisioned in this RFP.

  - Testing Approach

- Offerors are to provide a detailed narrative of the testing approach proposed that includes but is not limited to:

- Configuration Testing

- Integration Testing

- Interface Testing

- Performance, Capacity and Stress Testing

- Regression Testing

- Business Continuity and Disaster Recovery Testing

- User Acceptance Testing

- Security Testing

- Any Federal Government required Testing

Offerors are to add to the above list other testing phases / types recommended by the Offeror.  For each test type/phase, provide a narrative or table of the responsibilities of the Offeror and the Authority personnel, how long the testing is expected to take (in duration) and what tools and techniques the Offeror proposes to use to assure that testing is thorough and that quality issues are detected and remediated at the earliest possible stage of testing.

  - Roles and Responsibilities

Offerors are to provide a clear identification of what roles and responsibilities entities other than the Offeror need to provide in order to enable the Authority to run a comprehensive ACA compliant, cost-effective exchange with high customer satisfaction.  At a minimum, the Authority intends to undertake roles and responsibilities related to marketing, outreach, in-person assister training, and broker certification functions. The Offeror shall complete the table below considering all aspects of this RFP in combination with all Federal and State requirements related therein:

| Function | Responsible for Technology Platform | Responsible for Facility and Other Tangible Good | Responsible for Business or Technical Operations |
| --- | --- | --- | --- |
| List all functions in following rows | List either “Commonwealth”, “Offeror”, or “Other” | List either “Commonwealth”, “Offeror”, or “Other” | List either “Commonwealth”, “Offeror”, or “Other” |

Note:  It is expected that this table will contain numerous rows to cover every function. Where a single row addresses multiple functions please indicate so.  Also, if responsibility is “Shared” or “Supporting” indicate so (e.g. “Offeror supporting Commonwealth” or “Offeror shared with Commonwealth”)

  - Timeline and Deliverables

The Offeror’s proposal shall describe the strategy for accomplishing the goals outlined in each phase of Section 6 and provide a proposed timeline, in Gantt format, for the accomplishment of the goals, with the SBE being operational no later than November 2020. If the Offeror identifies any deficiencies in the Authority’s prospective project plans, then the deficiencies and the Offeror’s suggested resolution shall also be described.

Similarly, if the Offeror would require additional time to implement the proposed solution, (e.g. to construct a new call center location or hire/train additional staff), these requirements shall be defined in the proposal.

  - Required Non-Services Items

Identify the name and describe in detail all non-services that need to be provided in order to meet or exceed all requirements stated in the RFP and the related deliverables, tasks and timelines.  This includes, but is not limited to, all software, hardware, facilities, physical materials, licenses, maintenance agreements or any other non-personnel items necessary to provide the functions listed in Sections 5 and 6.  Additionally, for each item listed, Offerors are to clearly indicate if the Offeror will be providing the item or if the Offeror is not including the item, what entity they expect will be providing the item. Preference of the Authority is that the Offeror provides all necessary material and services necessary to fulfill the requirements of the RFP.

Where a non-service item is listed, and such item involves a license agreement, Offerors are to provide a copy of the license for the Authority’s review as part of this RFP response.

  - Considerations for Changes

- The Authority expects that during the course of the project there will be changes to the scope, timeline or other changes to the contracted work which will have to occur.  Offerors are to provide a detailed explanation of an approach to anticipating and addressing these situations without impacting the contract.  To this end, Offerors are to provide a recommended solution to this challenge.  Examples might be, but are not limited to; Bank of Hours, Contingency Funds, etc.  In responding to this response requirement, Offerors are to describe the approach.  However, any information relating to cost should only be contained within the Cost Response as described in Section 7.

  - General Constraints

Describe in detail how the proposed solution will operate within the constraints identified in Section 5.1.5 and meet all of the requirements in Section 5 of this RFP.

  - Emergency Preparedness.

To support continuity of operations during an emergency, including a pandemic, the Commonwealth needs a strategy for maintaining operations for an extended period of time. One part of this strategy is to ensure that essential contracts that provide critical business services to the Commonwealth have planned for such an emergency and put contingencies in place to provide needed goods and services.

    - Describe how you anticipate such a crisis will impact your operations.

    - Describe your emergency response continuity of operations plan. Please attach a copy of your plan, or at a minimum, summarize how your plan addresses the following aspects of pandemic preparedness:

    - Employee training (describe your organization’s training plan, and how frequently your plan will be shared with employees);

    - Identify essential business functions and key employees (within your organization) necessary to carry them out

    - Contingency plans for:

- How your organization will handle staffing issues when a portion of key employees are incapacitated due to illness; and

- How employees in your organization will carry out the essential functions if contagion control measures or other circumstances prevent them from coming to the primary workplace.

    - Describe how your organization will communicate with staff and suppliers when primary communications systems are overloaded or otherwise fail, including key contacts, chain of communications (including suppliers), etc. and;

    - How and when your emergency plan will be tested, and if the plan will be tested by a third-party.

- technical requirements

  - General Requirements

    - Overall Requirements

The solution proposed must recognize that the proposed solution shall be required to comply with all federal requirements related to the establishment and operation of an SBE under the ACA, including but not limited to those requirements detailed in 45 C.F.R. Subt. A, Subch. B Part 155.

    - Support to the Authority

The Selected Offeror shall support the Authority in its interactions, approvals, and data submittals to all Federal and State oversight and sponsoring agencies, such as but not limited to CMS, Auditors, etc.  Support includes preparation for and attendance at meetings, Blueprinting, approvals for ATC, Federal or State audits, and any other requirements or requests by such agencies.

    - Standards.

The Selected Offeror must adhere to all applicable federal and state laws, regulations, rules, policies and standards relating to the exchange as may be modified during the term of the contract, including Commonwealth and Authority mandates and standards for required hardware, software, and development components. In addition, the Selected Offeror must have a working knowledge of all federal, Commonwealth, and PID or Authority mandates, regulations, standards, and requirements that apply to this project, including operational compliance with any applicable legislation passed at the federal level throughout the term of the contract. The Selected Offeror must pass or remedy all respective audits, including those conducted by the Commonwealth, the federal government, and other auditing sources, such as the statement on standards for attestation engagements (“SSAE”) 18 SOC 1. If applicable laws, regulations, rules, policies or standards are changed during the contract term, the Authority and the Selected Offeror will engage in the process described in the contract standard terms and conditions. The Selected Offeror must adhere to all federal, Commonwealth, Authority and Department mandates and standards.  IRS Pub 1075 has many requirements for the receiving, storing, and accessing of FTI data including background checks for personnel and audit requirements.   The selected offeror will be expected to meet the requirements of IRS Pub 1075 and work cooperatively with the HHSDC Chief Security Officer on any impacts to Commonwealth agencies or systems.

    - Capacities

The proposed solution’s support for all capabilities and requirements identified in Section 5 must be capable of servicing at least a 20% increase in user and participant capacity over the figures presented in Section 1.6 of this RFP.  In addition, the system, including the supporting infrastructure, must be scalable and be able to increase the system's capacity as its processing load and/or demand grows.

Additionally, the proposed solution shall be able to accommodate the temporary increases in volume of customer’s applications and / or inquires during peak time such as Open Enrollment or in situations where there have been other external events affecting consumer needs for health insurance.

    - Communications and Correspondence

- The proposed solution shall support the Authority’s needs to communicate with its customers, business partners, contractors, the Federal Government, and any other external entities essential to the operation of all aspects of the solution defined herein.  This includes, but is not limited to email, physical mail, in-person interactions, chat, telephone, etc.  Such communications will include both in-bound and out-bound communications.

- Additionally, such communications and correspondence shall support multiple languages as dictated by applicable State and Federal laws in both written form and verbal (e.g. translation services, language lines, etc.)

    - General Constraints.

The proposed solution shall address all of the following platform constraints:

- Disruption to existing business processes of the Pennsylvania Medicaid administering agency, the Department of Human Services (“DHS”), is undesirable. DHS currently serves over 2.3 million Medical Assistance and CHIP recipients. The proposed solution shall provide independent functionality for all SBE functions listed in Section 5.2 and shall mirror the current integration model between DHS and the federal platform.  The proposed solution shall be capable of sending outbound account transfers to the DHS system and receiving inbound account transfers from the DHS system utilizing the same business rules, data formats, and transfer protocols as its current integration with the FFE.

2.	Immediate integration with the DHS system presents an undesirable risk of disruption and is therefore not being sought; however, the Authority supports an eventual path towards a statewide “No Wrong Door” model in which eligibility and user authentication functions would be shared between Commonwealth agencies. The proposed solution must be capable of modular integration of these functions with minimal changes to the solution’s codebase. This level of integration is not intended to be pursued at this time; the intent of the question is to assess the readiness of the solution to facilitate such an integration in the future.

3.	The proposed solution shall be capable of receiving an account transfer from DHS after a determination of ineligibility for Medical Assistance.  If not currently supported by the proposed solution, please describe the changes required to accommodate such an integration.

4.	The proposed solution shall support user authentication and authorization services administered from a remote system, for example using secure web services. Appendix F 1.b describes the Commonwealth requirement for the Selected Offeror to utilize the Keystone Login for authentication and authorization to Commonwealth systems.  Describe the architecture and implementation of the solution’s authentication and authorization system, and any changes required to accommodate remote administration via Keystone Login.

5.	DHS maintains Pennsylvania’s current authority to connect to the FDSH. The proposed solution shall be capable of both establishing a separate connection with the FDSH without relying upon the DHS connection and be capable of relying upon the DHS connection should the need arise.

6.	DHS does not utilize FTI data to verify income. Inbound account transfers from DHS (i.e. Medical Assistance referrals) will include income data from one of the following sources: (1) Equifax Work Number, (2) State Wage Information Collection Agency (“SWICA”) income data, or (3) consumer-provided documentation; the account transfer will include the income data, but not the source of the data. The Authority is currently seeking CMS approval to use this income data—in lieu of IRS income data—for APTC/CSR eligibility calculations.  The proposed solution should be capable of utilizing either the FTI or the verified income data included with inbound account transfers for APTC/CSR eligibility calculations.

7.	Processing of consumer payment transactions, including binder payments, is expressly out of scope for this project.  The proposed solution shall fully support the sole processing of consumer payment transactions by Pennsylvania’s on-Exchange insurance carriers.

8.	Disruption to existing business processes of Pennsylvania on-Exchange insurance carriers is a risk. The proposed solution shall be capable of interfacing with carriers in the same manner as the current integration with the FFE.  The proposed solution shall directly interface with private insurance carrier systems using the same business rules, data formats, and transfer protocols as the FFE.  The proposed solution shall be capable of loading certified plan data from the System for Electronic Rates & Forms Filing (“SERFF”).  The Selected Offeror shall be solely responsible for working with and assisting all on-Exchange insurance carriers with the development, testing, establishment and maintenance of any interfaces with such carriers necessary for the operation of the SBE.  The Selected Offeror shall establish and maintain a single point of contact for the on-Exchange insurance carriers, and that point of contact shall be responsible for ensuring that the carrier interface requirements for the SBE are met and addressing any questions and requests from the carriers.

  - Health Insurance Exchange Technical Platform Requirements.

    - Functional Requirements.

The configuration of the platform in an Offeror’s proposed solution shall have successfully supported a significant portion of the operations of at least one ACA-compliant health insurance exchange over the course of at least one complete Plan Year.  The proposed solution shall be capable of concurrently supporting each of the following functions, and should have supported all of the following functions for a single SBE within a single plan year:

- User authentication/authorization.

- Anonymous pre-screening of eligibility.

- Anonymous plan comparison.

- Eligibility determination, including calculation of advance premium tax credit (“APTC”) and cost-sharing reduction (“CSR”) subsidies.

- Plan comparison/consumer decision support.

- Individual QHP and SADP enrollment during open enrollment period (“OEP”) and special enrollment period (“SEP”).

- Small business health options program (“SHOP”) enrollment during OEP and SEP.

- Verification of SEP/qualifying life event (“QLE”) eligibility.

- Data persistence.

- Electronic data interchange (“EDI”) with state Medicaid agency.

- EDI with insurance carriers

- EDI with Federal Data Services Hub (“FDSH”) to support verification information.

- Plan preview for carriers during recurring data correction windows.

- Consumer messaging via U.S. mail.

- Consumer messaging via email.

- Consumer messaging via short message service (“SMS”).

- Eligibility appeals processing.

- Consumer complaint resolution.

- Customer relations management (“CRM”).

- All applicable Financial Management and Accounting.

- Insurance Carrier reconciliation.

- 1095 form production.

- 1095 form delivery via U.S. Mail.

- Electronic reporting to United States Internal Revenue Service (“IRS”).

25.	Electronic reporting to United States Department of Health and Human Services, Centers for Medicare and Medicaid Services (“CMS”).

    - Other Heath Insurance Exchange Technical Requirements.

The proposed solution shall have all the following technical capabilities and meet all of the following technical requirements:

- Migration of existing consumer data from the FFE via secured file transmission to the proposed platform, including development of the requirements for the data migration, communicating these requirements to the appropriate stakeholders, and coordinating the data transfer from CMS.

- Migration of existing consumers from the FFE via secured file transmission to the proposed solution while maintaining existing relationships between consumers, their respective insurance carrier and QHP/SADP identifications, their FFE-assigned health insurance exchange (“HIX”) identifications, and—if applicable—their respective enrollment professionals using the National Producer Number (“NPN”) code.  Describe the dependencies and requirements for such a migration, including any required consumer follow-up activities (such as but not limited to re-verification of user accounts).

- Utilize the Commonwealth’s Keystone Login for consumers to login into the proposed solution for the SBE, and comply with the requirements of the Commonwealth’s Customer Service Transformation Standards attached hereto as Appendix F.   The offeror should describe a strategy to migrate data to the new users accounts in a manner that they are ready for eligibility re-verification and auto re-enrollment for Plan Year 2021 including any requirements or dependencies not defined in this RFP.  The strategy should also include a communication plan to citizens if required.

- Dedicated portals for consumers; consumer assistance center workers; Authority administrative staff; brokers, agents, and navigators; and insurance carriers.  Include a detailed description of each user role’s user interface, capabilities, and limitations; role playing capabilities for administrative users should also be described.  These portals should use Commonwealth user directories rather than maintaining a separate user repository and authentication within the solution.

- Provide an intuitive and responsive graphical user interface (“GUI”) capable of supporting a wide range of desktop and mobile computing devices.  The design must follow Commonwealth branding as described in Appendix F Section 2

- Compliance with all applicable requirements defined in Title II of the Americans with Disabilities Act (“ADA”) and all applicable guidelines defined in the Web Content Accessibility Guidelines (“WCAG”) version 2.0.

- Compliance (including facility) with MARS-E 2.  The facility should meet or exceed a Tier 4 uptime rating.

- Include the Offeror’s preferred hosting provider and describe the geographical location of the provider’s data center(s).  Describe redundancies and disaster mitigation safeguards implemented by the provider and indicate whether or not data center(s) can be located entirely within the Commonwealth of Pennsylvania.

- Safeguard personally identifying information (“PII”) and federal tax information (“FTI”) by encrypting user data, both in transit and at rest.

- Minimize the persistence of sensitive data.  Describe in detail the proposal’s process for minimizing the persistence of data returned from the FDSH.

- Support geo blocking to prevent system access from outside of the United States.

- Comply with all of the Requirements for Non-Commonwealth Hosted Applications/Services, as attached in Appendix B.

- All hardware and software shall be kept current with the supplier’s latest supported software releases both during implementation and during all subsequent Hosting, Maintenance and Operations years.  This includes but is not limited to, the Operating Systems, all Third-Party software, all Selected Contractor provided software, all tools and non-operating software (e.g. monitoring tools, project management tools, reporting tools, etc.) etc.

If the Offeror plans to utilize a cloud service provider to host the solution, the Offeror must submit as part of their proposal relative to Section 5 a completed Cloud Use Case Questionnaire, attached hereto as Attachment E.

  - Consumer Assistance Requirements.

    - Consumer Assistance Technical Requirements

The proposed solution shall support the following consumer assistance functions:

- Customer relations management.

- A comprehensive telephony system for handling calls, chat, call routing, integrated voice response, queuing, and generating reports for monitoring performance.

- Direct enrollment of consumers.

- QLE/SEP eligibility verification.

- Resolution of Data Matching Issues (DMI)/FDSH exceptions.

- Use account maintenance support.

- Ticketing to record incidents, questions, issues and resolution.

- Ticket escalation.

- Basic consumer complaint resolution (i.e. Tier 1 support).

- Escalated consumer complaint resolution (i.e. Tier 2 support).

- Broker/Navigator support.

- Assister support.

- Insurance carrier support.

- Eligibility appeals processing.

    - Consumer Assistance Center Functional Requirements.

In addition to the technology platform described in Section 5.2 and 5.3 of this RFP, the Authority is seeking the same Offeror to provide a superior and experienced consumer assistance center and related business operations.  Offerors’ technical proposals should proactively identify any missing requirements or constraints, or any requirements or constraints in need of modification or clarification.

The Authority is seeking a proven solution which has successfully supported the consumer assistance functions of at least one SBE over the course of at least one complete Plan Year. The Authority desires an Offeror with direct experience supporting an SBE, but any relevant experience supporting an ACA-compliant health insurance Exchange will be considered.

The proposed solution should include both the technology, processes, policies and personnel required to provide all of the following functions to the SBE’s consumers:

      - Consumer education for ACA requirements/eligibility.

      - Consumer education for Medical Assistance/CHIP mixed household eligibility.

      - Customer relations management.

      - Direct enrollment of consumers.

      - QLE/SEP eligibility verification.

      - Resolution of Data Matching Issues (“DMI”)/FDSH exceptions.

      - User account maintenance support.

      - Routing and referrals to appropriate agencies or other entities for inquires beyond the scope of the Authority (e.g. consumer complaints, etc.) through resolution.

      - Ticketing to record incidents, questions, issues and resolution.

      - Ticket Escalation.

      - Basic consumer complaint resolution (i.e. Tier 1 support).

      - Escalated consumer complaint resolution (i.e. Tier 2 support).

      - Producer/Navigator support.

      - Assister support.

      - Insurance carrier support.

      - Eligibility appeals processing.

      - Informal appeals resolution.

      - Attendance at, and assistance with appeals hearings.

      - Customer satisfaction surveys.

      - Processing of incoming mail.

      - Quality assurance.

      - Staffing (including staffing qualifications), scheduling, and workforce management.

      - Training of consumer assistance center staff.

      - Caseload forecasting.

      - Monitoring of benchmarks/performance indicators.

      - Reporting of benchmarks/performance indicators.

      - Security/privacy oversight and monitoring such as but not limited to HIPAA, Physical security, cyber security, etc.

    - Consumer Assistance Center Technical Requirements

- The Selected Offeror shall provide a telephonic system, including Interactive Voice Response functionality

- The Selected Offeror’s IVR telephonic system shall provide content specific messages in English and Spanish to consumers based on caller response on a 24/7/365 basis

- The Selected Offeror’s system shall be equipped with a telecommunications device and/or service for the hearing impaired.

- The Selected Offeror shall provide consumers with translation services with as minimal an interruption to the call as possible.  The cost of these services is part of the overall costs for the Consumer Assistance Center.

- The Selected offeror shall be equipped with an Automated Call Distribution System that includes the ability to: monitor and report on real-time historical Consumer Assistance Center activity, generate reports on call volume, average wait time, average talk time, abandoned calls and other statistics.

- The Selected Offeror’s ACD system should have the ability to record incoming and outgoing calls for quality assurance.

- The Selected Offeror shall have the ability to offer customer satisfaction surveys to gather caller feedback. The survey shall be approved by the Authority and results reported to the Authority on a monthly basis.  (the specifics of what you require must be defined).

- The Selected Offeror shall have the ability to transfer consumers to other commonwealth agencies as appropriate and minimize the need for the consumer to dial multiple numbers.

- The Selected Offeror shall support normal business hours of operation of Monday-Friday 8:00AM EST/EDT not including State holidays.  Additionally, the Selected Offeror shall be able to expand those hours during critical times such as but not limited to Open Enrollment.

- The Selected Offeror shall establish a public inquiry phone number which will be owned by the Authority after the contract ends.

    - Other Consumer Assistance Center Requirements.

The proposed solution shall satisfy all of the following specific requirements:

1.	Consumer assistance personnel shall utilize the technology platform to support the functions defined in Section 5.

- Support interactions with non-English speakers

- The Selected Offeror shall have the ability to increase staffing levels to ensure adequate customer service is provided at all times, especially during peak season

- Name and describe in detail the software and hardware utilized to provide the functions listed in Section 5.

- Describe the benchmarks and performance indicators (including target levels) implemented by the proposed solution to ensure a consistent level of customer satisfaction throughout the plan year.

- The Offeror shall increase staffing levels as necessary to ensure that benchmarks and target performance levels as established by the Authority are met during OEP and year-round.

- The Offeror shall appropriately train and certify all consumer assistance personnel for the secure handling and processing of sensitive information, including PII, FTI (in accordance with IRS Pub 1075), and Health Insurance Portability and Accountability Act of 1996 (“HIPAA”)-protected data. Describe the process for screening (if applicable), training, and certifying consumer assistance personnel.

- The proposed solution should record all phone conversations and electronic signatures and make those recordings easily available to call center and Authority staff members for a length of time consistent with the Commonwealth’s Record Retention requirements.  The telephone call must also capture, store and provide retrieval of recorded signatures as required by the ACA.  The solution should also allow for the long-term archival of recordings consistent with Commonwealth record retention requirements.

- The proposed solution shall allow for the real-time monitoring of phone conversations by call center supervisors/trainers or Authority staff.

- The proposed solution shall assure that consumer assistance personnel comply with the substantive requirements of 40 P.S. §4404 (navigator and exchange assister scope of activity).

    - Consumer Assistance Center Constraints.

The consumer assistance center is anticipated to receive inquiries from consumers for Plan Year 2020 prior to operation of the SBE for Plan Year 2021.  Offerors shall ensure that these inquiries are quickly identified and appropriately routed to the FFE call center.  Describe in detail how the proposed solution will operate within the above-mentioned constraints and meet all of the above-mentioned requirements.  The proposal must recognize that the proposed solution shall be required to comply with all federal requirements related to the establishment and operation of an SBE under the ACA, including but not limited to those requirements detailed in 45 C.F.R. Subt. A, Subch. B Part 155 and be capable of servicing at least a 20% increase in capacity versus the figures presented in Section 1.6 of this RFP.

  - Mail Operations

    - Mail Operations

The proposed solution shall support the following mailroom functions:

- Electronic Document Management – ability to capture, produce, and manage electronic documents, including electronic documents resulting from scanning of paper documents.

- Integration of Electronic Document Management with Consumer Assistance Center systems – including the ability to simultaneously access and view structured data about a customer, electronic copies of documents sent by the customer to the Exchange, and electronic copies of documents sent by the Exchange to the customer.

- Document Date/Time Stamping, Unique Identification and Indexing – including linking documents to a particular consumer, broker, and other pertinent entity with which the Exchange will transact.

- Attachment Inserts – Ability to insert attachments into outbound mail for Outreach and Education purposes, e.g. fliers associated with specific campaigns.

- Postal Zip Sort – Ability to optimize postage costs by leveraging reduced postal rates for Pre-Sort.

- Document Delivery via Multiple Channels – Support delivery of documents using the method preferred by a recipient, e.g. printing/mailing vs. e-mailing, in accordance with pertinent laws and regulations.

- Mailroom personnel shall utilize the technology platform to support the functions defined in this Section 5.4.

- The Offeror shall increase staffing levels as necessary to ensure that benchmarks and target performance levels are met during each OEP and year-round.

- The Offeror shall appropriately train and certify all mailroom personnel for the secure handling and processing of sensitive information, including PII, FTI, and Health Insurance Portability and Accountability Act of 1996 (“HIPAA”)-protected data. Describe the process for screening (if applicable), training, and certifying mailroom personnel.

- The Offeror shall conduct real-time monitoring of mailroom operations to ensure adherence to all applicable requirements including information security and privacy and confidentiality assurance requirements as well as security audit requirements.

    - Mailroom Technical Requirements.

In addition to the technology platform described in Section 5.2 and 5.3 of this RFP, the Authority is seeking the same Offeror to provide a superior mailroom operation as specified in Section 5.4.  Offerors’ technical proposals should proactively identify any missing requirements or constraints, or any requirements or constraints in need of modification or clarification.  The Authority is seeking a proven solution which has successfully supported a mailroom of at least one SBE or a similar operation over the course of at least one year. The Authority desires an Offeror with direct experience supporting an SBE, but any relevant experience supporting an ACA-compliant health insurance Exchange will be considered. The proposed solution should include both the technology and personnel required to provide all of the following functions:

- Ability to process all in-bound mail and faxes, and electronic documents.

- Digitization of each document.

- When applicable, link documents to a particular customer and use that customer index throughout the mail, printing, and digitization process. This will involve using a standard naming convention and allowing viewing and processing by staff.

- Ability to refile/re-index documents.

- Ability to destroy printed media once a digitized version of the corresponding documents has been created and deemed valid.

- Ability to back-fill legacy documents into a customer’s document folder.

- Timeline and Deliverables.

The delivery of the online health insurance exchange technology platform required by this section shall be divided into three phases: (1) design, development, and implementation (DDI) or more accurately analyze, configure and deploy (ACD – see Section 1.1 – Terminology and Acronyms for clarification); (2) transition to operation as an SBE (Technology Transition (TT)); and (3) autonomous, ongoing maintenance and operations as an SBE (M&O). Phases one and two are further divided into distinct stages.

  - Overall Deliverables

The following sections detail the deliverables associated with each stage and phase anticipated to be provided by the Offerors.  This section identifies those deliverables which are not stage or phase specific.

    - Overall Integrated Project Schedule and Timeline

The Integrated Project Schedule will demonstrate that the Offeror has a thorough understanding of the Scope of Work and what must be done to satisfy the project requirements and will reflect the Authority’s desire for a phased approach to implementation. The Integrated Project Schedule must include detail sufficient to give the Authority an understanding of how the Offeror intends to:

- Manage the work to guarantee scope, schedule and budget are met;

- Guide work execution;

- Utilize Contractor resources for certain project activities;

- Rely on the Authority, Commonwealth agency, and business partner resources for certain project activities;

- Document assumptions and decisions;

- Document risks, issues, and contingencies;

- Facilitate communication among stakeholders; and

- Define key management review as to content, scope, and schedule.

The Integrated Project Schedule shall be constructed in accordance with industry standards, accepted project management principles outlined in the Project Management Body of Knowledge (PMBOK) from the Project Management Institute (PMI), or acceptable equivalent. Additional criteria for the Integrated Project Schedule are reflected in the following:

- The Integrated Project Schedule shall include, at a minimum: a three-level work breakdown structure; project milestones; and deliverables.  Furthermore, the Integrated Project Schedule must address implementation of each phase of the project.

- The Integrated Project Schedule shall also incorporate all locations including Commonwealth locations where the Contractor proposes to perform work associated with the project.

- For this project, it will be crucial to coordinate activities and resources with pertinent Authority and other Commonwealth staff, including DHS staff.  Thus, in its Integrated Project Schedule the Contractor must clearly specify deliverables and dates that require the Authority’s involvement for technical setup and project environments and the involvement of the Authority’s and other Commonwealth staff and business partners, including DHS staff, in implementation activities.

- The Contractor must build, produce, maintain and monitor the project Integrated Project Schedule in Microsoft Project.

The Integrated Project Schedule shall describe the Offeror’s process to complete each major project phase (i.e., Project Initiation; Requirement Elaboration and Specification Definition; Build: Configuration, Customization and Integration; Testing; Knowledge Transfer and Training; Data Conversion and Migration; Deployment: Cutover and Acceptance; and Implementation Closeout).  This will include the proposed project management methodology, milestone schedule, staffing plan and organizational chart. The Integrated Master Project Schedule should also indicate the delivery dates for each subsequent deliverable in this RFP.   The Offeror must deliver the initial Integrated Master Project Schedule within 45 days after the contract effective date.

    - Functional Specifications Deliverables

Functional Specifications Documents (tied to Requirement Elaboration and Specification Definition):  Subsequent to project initiation, the Offeror will undertake requirement elaboration and specification definition activities including but not limited to design sessions/workshops with the Authority and other Commonwealth personnel and business partners. This will require the discovery and documentation of current business practices, including mapping and workflows for all aspects of the project identified in the RFP.  This work will include eliciting and documenting input from stakeholders to gain an understanding of user requirements and needs, work across teams to identify new workflows, and determine the user priorities of the system.  The Offeror must be conversant with the Authority’s business environment to address potential roadblocks, challenges or risks.  A gap analysis is required to determine the differences and distinctions between current practices and proposed system features and functions, and solutions to those gaps.  Starting point should be functional requirements from an SBE where the solution has been implemented.

The aim of Requirement Elaboration and Specification Definition is to clearly outline the detailed design and configuration of the solution and identify any required customization. This task must be completed in accordance with the dates set forth in the approved Integrated Project Schedule and must:

- Identify required product modifications and delivery dates,

- Determine interface requirements and delivery dates, and

- Modify the Integrated Project Schedule as deemed appropriate.

The solution shall be implemented in a manner that will allow for the evolution of operations and business practices with minimal impact and rework. As a result of these activities, the implementation and deployment plans may need to be modified.

It is expected that, as part of this task, the Offeror will engage in analysis of current-state processes and recommendations regarding changes to these processes or the engineering of entirely new processes with the goals of facilitating implementation and enabling improvements in organizational performance, work processes and related outcomes, and customer service.

    - Requirements Traceability Matrix

A detailed functional requirements traceability matrix shall be created and maintained throughout the project’s stages and phases.  The matrix will be completed in accordance with the dates set forth in the approved Integrated Project Schedule. This matrix will reflect the actual configuration required to implement the system.  This matrix will be used throughout the life of the project, including acceptance testing.

    - Testing Plan

The Offeror must demonstrate through a formal, prior-approved testing process that the solution performs as required from various remote facilities and that the system meets or exceeds the Authority’s functional and technical requirements.  The testing process will incorporate all levels of testing: unit/module, integration, system and end user acceptance, in coordination with CMS regulations.  The Offeror and the Authority shall mutually develop specific written criteria for any testing that will objectively measure each functional and technical requirement.

The Offeror will submit a comprehensive Testing Plan to the Authority in accordance with the dates set forth in the approved Integrated Project Schedule.   The Authority anticipates considerable collaboration with the Offeror in the plan’s construction. Testing will include all software components in accordance with published functions and features, based on business scenarios and user friendliness.  Interfaces will be tested based on design and business scenario.  At a minimum, the test plan must incorporate unit, integration, usability, performance, interface (including testing with DHS, CMS, and insurance carriers), load, fail-over and security vulnerability and penetration tests.

For each of the various types of tests that will need to be performed – at a minimum, unit, integration, system, performance, stress and security testing - the Testing Plan must outline the following:

  - Scope;

  - Objective;

  - Roles and Responsibilities;

  - Test Schedule;

  - Test Execution Protocol/Workflow;

  - Assumptions for Test Execution;

  - Constraints for Test Execution;

  - Test Scripts – these must be tied to functional requirements;

  - Test Data Requirements;

  - Test Resource Requirements;

  - Expected Results;

  - Acceptance Criteria (including item pass/fail criteria);

  - Testing Status Reports;

  - Phase Completion Reports;

  - Test Final Report Sign-Off;

  - Testing Facilities;

  - Testing Tools;

  - Defect remediation Process.

6.1.5	Risk and Issues Management Plan

The Offeror must design, implement, maintain and monitor a Risk and Issue Management Plan to identify and mitigate risk early. The Offeror must apply an industry standard risk management methodology. The Risk and Issue Management Plan will include the following:

1.	Issue Tracking Tools;

2.	Issue Severity and Priority Definition;

3.	Issue Reporting

4.	Issue Tracking;

5.	Risk Mitigation;

6.1.6    Defect Management Plan

The Offeror must identify and resolve defects pertaining to the SBE identified during testing as well as during production after implementation. The Offeror is responsible for overall defect management for the SBE and will develop the Defect Management Plan to document the process to identify, report, track, monitor, and resolve defects identified during testing and production to the Authority. The selected Offeror must have a tool (such as ServiceNow or Team Foundation Server) that allows for the reporting, tracking, and monitoring defects and resolution timeframes.   The chart below indicates the Severity of defects for categorization during testing and remediation timeframes in production (Attachment F – Service Level Agreements and associated Liquidated Damages.

- Deliverable:  Defect Management Plan (See Attachment F.4 for details)

- 6.1.7	Training Plans

The Offeror shall conduct on-site knowledge transfer and training activities for the Authority’s project team and system administrators and the end users.  The aim of Knowledge Transfer and Training is to ensure that the Authority’s staff, including administrators and end users, have the knowledge and documentation to use and support the solution beyond implementation.

The Offeror shall discuss and reach agreement with the Authority on the optimal staging and provision of knowledge transfer and training activities.

The Offeror will develop and execute, in cooperation with the Authority, a Training Plan that will be approved by the Authority. The plan should be completed in accordance with the dates set forth in the approved Integrated Project Schedule and shall outline separate, detailed approaches for at least two distinct audiences: system administrators and end users.

For each audience, the Training Plan shall include at a minimum:

- A recommended approach or approaches to knowledge transfer (system administrators) or training (end-users); the approaches should be designed for adult learners possessing a variety of backgrounds, experiences, and learning styles and should recommend approaches for an organization of the Authority’s size and complexity;

- A recommended approach to acquired skills assessment;

- An inventory of tasks, deliverables and resources necessary to complete the knowledge transfer or training effort, including tools and documentation necessary to support the proposed effort; and for each method or course:

- A course description;

- The target audience (system administrator, end user or other);

- Proposed training goals;

- Proposed training standards;

- The specific plan for training relevant personnel;

- The delivery timeframe (by phase, implementation step) with a strategy for providing training early in the project to allow the training goals to be implemented throughout the project life cycle;

- A description of training deliverables and format (i.e., online, written documentation, course materials); and

- A description of skill sets achieved at the end of training and how training effectiveness will be measured and addressed.

    - System Security Plan

The selected Offeror will maintain compliance with Security requirements in Appendix B of the RFP and with Commonwealth Information Technology Policies in Appendix C and the Terms and Conditions, as well as compliance with the requirements of the CMS MARS-E 2.0 framework and all deliverables required System Security Plan and Plan of Action and Milestones (POAM).

The selected Offeror must describe how its cyber security plan monitors, identifies and prevents cyber security incidents and rectifies cyber incidents that occur.  The selected Offeror must describe the process and tools used to ensure that the product is protected against cyber threats and penetration.

The selected Offeror must detail how it will enforce security within the proposed solution and the selected Offeror’s organization, including physical security of hardware, identification of individuals who have privileged access, and how data to and from external sources is controlled.  A discussion of compliance with federal regulations including HIPAA should also be included.

The Offeror will submit a System Security Plan to the HHSDC Chief Security Officer and the Authority for approval.

    - Change/Release Management Plan.

The goal of the Authority is that customized changes to the proposed solution should be minimal.  However, if changes are required, the Offeror must document a process to request changes to the proposed solution.  This process must include the submission of the request for change, estimation work products including estimated hours, cost and timeline.  The Offeror should explain its process for how changes are evaluated and prioritized. Additionally, it must also describe the process and documents that will be provided during the development lifecycle (i.e. requirements matrix, design documents, testing and training plans, operational readiness checklists) for the Authority review and approval.

The Offeror should also address the following in this plan:

- The process for determining how changes, customizations and/or configuration changes. are evaluated for inclusion into the product.

- The process for testing and implementing product releases for the proposed solutions

- The rollback process and procedure for any changes that are not successfully implemented

- Any existing release and/or maintenance schedules for the proposed solution and if there is a process for implementing changes outside of these schedules.

- Differences or deviations from the Change/Release Management plan for configuration changes deemed necessary by the Authority, as opposed to product or customized changes, to the proposed solution.

  - Technology Platform Phase One - DDI.  DDI will encompass the following five distinct stages.

    - DDI Stage One.

- The Offeror, in coordination with the Authority, shall develop a detailed Project Plan for Technology Platform Phases One and Two.

- Offeror, in coordination with the Authority, shall work with representatives of DHS, Pennsylvania’s on-Exchange insurance carriers, CMS, Homeland Security, and the IRS to gather the technical and functional requirements for successful EDI with each external system. These requirements shall be used to create a detailed EDI Test Plan for each external system, to be furnished to the administrator(s) of each system.

- Offeror, in coordination with CMS, shall develop a detailed Data Migration Plan to ensure the successful migration of Plan Year 2020 consumers from the FFE to the proposed solution. The plan shall include technical requirements detailing the necessary format/data elements, to be furnished to CMS.

- Offeror, in coordination with Pennsylvania’s on-Exchange insurance carriers, shall develop a detailed carrier plan certification plan to ensure that carrier plan data is loaded from the SERFF system and made available for carrier review/correction during the limited data correction windows in July and September.

- Offeror, in coordination with Pennsylvania’s on-Exchange insurance carriers, shall develop a detailed consumer reconciliation plan to ensure that migrated consumer data from the FFE remains sufficiently in sync with subsequent enrollment, effectuation, and account maintenance transactions such that the migrated data can be utilized for eligibility re-verification and auto-reenrollment.

- All plans shall be developed in accordance with the principles of the Project Management Body of Knowledge (“PMBOK”). DDI Stage One is anticipated to commence upon the issuance of a Notice to Proceed by the Authority to the Selected Offeror and conclude within six months, contingent upon the Authority’s approval of deliverables.

- DDI Stage One Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of DDI Stage One:

- Project Plan and timeline for Technology Platform Phases One and Two.

- Technology Platform Annual Work Cycle Plan.

- EDI Interface Test Plans.

- Data Migration Plan.

- Carrier Plan Certification Plan.

- Consumer Reconciliation Plan.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of DDI Stage One.

    - DDI Stage Two.

i.	The Selected Offeror shall complete the initial customization and configuration of the technology platform, including the configuration of electronic interfaces to external systems; the configuration of a fully functional, sandboxed Exchange Testing Environment for use in subsequent stages of DDI; the configuration of a fully functional, sandboxed Exchange Training Environment for ongoing use by the Authority and consumer assistance center personnel; and the deployment of the customized codebase to the testing and training environments.

ii.	The Selected Offeror shall communicate the technical requirements for the EDI interface test plans to IT personnel from the Commonwealth and Pennsylvania’s on-Exchange insurance carriers.  The Selected Offeror shall provide the necessary support to ensure that those entities have the information and resources required to re-configure their existing FFE interfaces for use with the proposed solution. This support will also include leading testing coordination with external entities (Commonwealth agencies, CMS, insurance carriers).

iii.	DDI Stage Two Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of DDI Stage Two:

- Exchange Testing Environment.

- Exchange Training Environment.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of DDI Stage Two.

    - DDI Stage Three.

i.	The configuration of a fully functionally Exchange User Acceptance Test and Test for Production environment containing a copy of all software that is ready for deployment for UAT testing and verifying and testing production defects,

ii.	The Selected Offeror, in coordination with the external stakeholders defined therein, shall execute the EDI Test Plan developed in DDI Stage One. At the conclusion of DDI Stage Three the Selected Offeror shall deliver documentation certifying the complete and successful execution of the EDI Test Plan.

iii.	The Selected Offeror will develop a User Acceptance Testing (UAT) plan for use during DDI Stage Four.

iv.	DDI Stage Three Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of DDI Stage Three:

- Verified execution of EDI Test Plan.

- Verified implementation of UAT and related test environments

- UAT plan for use during DDI Stage Four.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of DDI Stage Three.

    - DDI Stage Four.

i.	The Selected Offeror in coordination with CMS, shall execute the Data Migration Plan developed during DDI Stage One, including the resolution of any data mismatches or outlier scenarios to the best of the Selected Offeror’s ability. At the conclusion of DDI Stage Four, the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Data Migration Plan, including, if applicable, detailed status information for data mismatches/exceptions and their resolutions.

ii.	The Selected Offeror will execute the UAT plan approved by the Authority during Stage Three and resolve any verified defects discovered during UAT.

iii.	DDI Stage Four Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of DDI Stage Four:

- Verified execution of Data Migration Plan.

- UAT approved by the Authority during DDI Stage Three, and a report of the results of the UAT, including identification of all discovered and resolved defects and a proposed resolution plan for any such discovered defects.  The expectation is that no defects will be implemented into production.

- Verification of resolution of any defects identified in the UAT.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of DDI Stage Four.

    - DDI Stage Five.

The Selected Offeror, in coordination with Pennsylvania’s on-Exchange insurance carriers, shall execute the Carrier Plan Certification Plan developed during DDI Stage One.  At the conclusion of DDI Stage Five, the Offeror shall have delivered documentation certifying the complete and successful execution of the Carrier Plan Certification Plan.

    - Selected Offeror, in coordination with Pennsylvania’s on-Exchange insurance carriers, shall execute the Consumer Reconciliation Plan developed during DDI Stage One.

    - At the conclusion of DDI Stage Five, the Selected Offeror shall have delivered documentation certifying the complete and successful execution of the Consumer Reconciliation Plan.

    - The Selected Offeror, in coordination with the Authority, shall develop and execute a Consumer Assistance Technology Readiness Plan to ensure optimal technical integration between the technology platform and the consumer assistance center. Upon completion the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Consumer Assistance Center Technology Readiness Plan.

    - The Selected Offeror, in coordination with the Authority, shall develop a Consumer Messaging Plan for the purpose of educating migrated consumers on the actions required for re-verification of their migrated user accounts.

    - The Selected Offeror shall develop a detailed Eligibility Re-Verification Plan to ensure a complete and accurate re-verification of migrated consumer eligibility.

    - The Selected Offeror shall develop a detailed Auto Re-Enrollment Plan to ensure a complete and accurate of re-enrollment of migrated consumers without an active plan selection during Plan Year 2021 OEP.

    - The Selected Offeror shall configure and deploy a public-facing Exchange Production Environment, inclusive of all resolved defects identified during UAT, and populated with the resultant consumer data from the executed Data Migration Plan.

    - The Selected Offeror shall develop a detailed User Reference Manual describing the complete feature set of the technology platform, including detailed instructions for the business processes supported therein, for use by the Authority and consumer assistance center staff.

    - DDI Stage Five Deliverables.

- The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of DDI Stage Five:

- Verified Execution of Carrier Plan Certification Plan.

- Verified Execution of Consumer Reconciliation Plan.

- Consumer Assistance Technology Readiness Plan (Technology Platform).

- Verified Execution of Consumer Assistance Technology Readiness Plan (Technology Platform).

- Consumer Messaging Plan (Technology Platform).

- Eligibility Re-Verification Plan.

- Auto Re-Enrollment Plan.

- Application Production Environment.

- User Reference Manual.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of DDI Stage Five.

  - Technology Platform Phase Two – TT.  TT will encompass the following three distinct stages.

    - TT Stage One.

    - The Selected Offeror shall ensure the continuous and ongoing availability and functionality of the Exchange Production Environment to support consumers and consumer assistance personnel with the re-verification of migrated user accounts, as defined in the Consumer Messaging Plan.

    - TT Stage One Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of TT Stage One:

- Such deliverables as determined by the Authority as being reasonably necessary for the completion of TT Stage One.

    - TT Stage Two.

- At the earliest practical date, the Selected Offeror shall make certified plan data available in the Exchange Production Environment to facilitate anonymous plan comparison by consumers.

- The Selected Offeror shall execute the Eligibility Re-Verification Plan developed during DDI Stage Five. At the conclusion of TT Stage Two, the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Eligibility Re-Verification Plan.

- TT Stage Two Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of TT Stage Two:

- Verified Execution of Eligibility Re-Verification Plan.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of TT Stage Two.

    - TT Stage Three.

- The Selected Offeror shall ensure the continuous and ongoing availability and functionality of the Exchange Production Environment to support Plan Year 2021 OEP.

- The Selected Offeror shall execute the Auto Re-Enrollment plan developed during DDI Stage Five. At the conclusion of TT Stage Three, the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Auto Re-Enrollment Plan.

- TT Stage Three Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of TT Stage Three:

  - Verified Execution of Auto Re-Enrollment Plan. Such other deliverables as determined by the Authority as being reasonably necessary for the completion of TT Stage Three.

  - Phase Three - M&O.

M&O is anticipated to commence upon completion of TT Phase Two and conclude at the end of the term of the contract resulting from this RFP.

- The Selected Offeror shall ensure the continuous and ongoing availability and functionality of the Exchange Production Environment.

- The Selected Offeror shall ensure the continuous and ongoing availability and functionality of the Exchange Training Environment.

- The Selected Offeror shall ensure the availability of the Exchange Testing Environment, as needed to verify and approve changes to the technology platform’s configuration (including change orders).

- The Selected Offeror shall ensure ongoing compliance with the responsibilities outlined in the Technology Platform Annual Work Cycle Plan.

- The Selected Offeror shall provide a detailed Technology Platform Annual Work Cycle Plan for ongoing maintenance and operations, inclusive of procedural, compliance, and regulatory milestones (inspection, certification, carrier plan data correction, reporting, auditing, etc.).

- The Selected Offeror shall perform all necessary maintenance and updates of the technical platform, as needed, and shall perform any requested upgrades or changes as directed by the Authority.

- Prior to the commencement of any upgrade or change to the Exchange platform, the Selected Offeror shall provide the Authority with a cost for the completion of such upgrade or change, the time required to complete the upgrade or change, any dependencies or contingencies involved in the upgrade or change, and any other information requested by the Authority.  No upgrade or change may occur without the express prior written authorization of the Authority.

  - Consumer Assistance Center Timeline and Deliverables.

Implementation of the Consumer Assistance Center requirements will be divided into three phases: (1) implementation of the consumer assistance center (Implementation), (2) transition support and consumer assistance during Plan Year 2021 OEP (Consumer Assistance Transition), and (3) autonomous, ongoing maintenance and operations of the consumer assistance center (Operations). Phases one and two are further divided into distinct stages.

    - Consumer Assistance Center Phase One - Implementation. Implementation will encompass two distinct stages.

- Implementation Stage One.

- The Selected Offeror, in coordination with the Authority, shall develop a detailed Project Plan and timeline for Consumer Assistance Center Phases One and Two.

- The Selected Offeror, in coordination with the Authority, shall develop a detailed Consumer Assistance Annual Work Cycle Plan, inclusive of procedural, compliance, and regulatory milestones (inspection, certification, reporting, auditing, etc.).

- All plans shall be developed in accordance with the principles of the PMBOK.

- Implementation Stage One Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Implementation State One:

  - Project Plan for Consumer Assistance Center Phases One and Two.

- Consumer Assistance Annual Work Cycle Plan.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of Implementation Stage One.

- Implementation Stage Two.

- The Selected Offeror, in coordination with the Authority, shall develop and execute a Consumer Assistance Center Technology Readiness Plan to ensure optimal technical integration between the technology platform and the consumer assistance center. Upon completion the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Consumer Assistance Center Technology Readiness Plan.

- The Selected Offeror, in coordination with the Authority, shall develop a Consumer Messaging Plan for the purpose of educating migrated consumers on the actions required for re-verification of their migrated user accounts.

- The Selected Offeror, in coordination with the Authority, shall codify standard operating procedures, as well as agreed-upon benchmarks and service-level targets, in a Consumer Assistance Center Standard Operating Procedures Manual.

- The Selected Offeror, in coordination with the federal healthcare.gov call center, shall develop and execute an Open Ticket Migration Plan to ensure that open tickets from the federal call center are successfully migrated to the consumer assistance CRM system in time for the consumer assistance center’s anticipated go-live date of September 01, 2020. Upon completion, the Selected Offeror shall deliver documentation certifying the complete and successful execution of the Open Ticket Migration Plan.

- The Selected Offeror shall prepare the consumer assistance center for operational readiness on September 01, 2020, including any required procurement, construction, hiring/training of staff, per the Project Plan for Consumer Assistance Center Phases One and Two that was developed during Implementation Stage One.

- Implementation Stage Two is anticipated to commence upon completion of Implementation State One and conclude on August 31, 2020, contingent upon the Authority’s approval of deliverables.

- Implementation Stage Two Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Implementation State Two:

- Consumer Assistance Technology Readiness Plan (Consumer Assistance Center).

- Verified Execution of Consumer Assistance Technology Readiness Plan (Technology Platform).

- Consumer Messaging Plan (Consumer Assistance).

- Consumer Assistance Center Standard Operating Procedures Manual.

- Open Ticket Migration Plan.

- Verified Execution of Open Ticket Migration Plan.

- Fully Staffed and Operational Call Center.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of Implementation Stage Two.

    - Consumer Assistance Center Phase Two: Consumer Assistance Transition. The Consumer Assistance Transition phase is anticipated to last four months, commencing on September 01, 2020 and concluding on December 31, 2020, and will encompass three distinct stages.

- Consumer Assistance Transition Stage One.

- The Selected Offeror shall begin providing full-capacity consumer support, including support for re-verification of migrated user accounts as defined in the Consumer Messaging Plan.

- The Selected Offeror shall begin ensuring compliance with the terms of the Consumer Assistance Center Standard Operating Procedures Manual.

- Consumer Assistance Transition Stage One is anticipated to commence September 01, 2020 and conclude September 30, 2020.

- Consumer Assistance Transition Stage One Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Consumer Assistance Transition Stage One:

- Such deliverables as determined by the Authority as being reasonably necessary for the completion of Consumer Assistance Transition Stage One.

- Consumer Assistance Transition Stage Two.

- Selected Offeror shall continue providing full-capacity consumer support, including consumer education to support the anonymous plan comparison process.

- Consumer Assistance Transition Stage Two is anticipated to commence October 01, 2020 and conclude October 31, 2020.

- Consumer Assistance Transition Stage Two Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Consumer Assistance Transition Stage Two:

- Such deliverables as determined by the Authority as being reasonably necessary for the completion of Consumer Assistance Transition Stage Two.

- Consumer Assistance Transition Stage Three.

- Selected Offeror shall provide full-capacity consumer support for Plan Year 2021 OEP.

- Consumer Assistance Transition Stage Three is anticipated to commence November 01, 2020 and conclude December 31, 2020.

- Consumer Assistance Transition Stage Three Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Consumer Assistance Transition Stage Three:

- Such deliverables as determined by the Authority as being reasonably necessary for the completion of Consumer Assistance Transition Stage Three.

    - Consumer Assistance Center Phase Three: Operations. Operations is anticipated to extend from the January 1, 2021 through the remainder of the term of the contract resulting from this RFP.

- The Selected Offeror shall ensure the ongoing provision of consumer assistance in accordance with the terms of the Consumer Assistance Center Standard Operating Procedures Manual.

- The Selected Offeror shall ensure ongoing compliance with the responsibilities outlined in the Consumer Assistance Annual Work Cycle Plan.

  - Mailroom Timeline and Deliverables.

Implementation of Mailroom requirements must be completed to support Plan Year 2021 OEP (and tied to Consumer Assistance Transition) and assumes post-Plan Year 2021 OEP ongoing maintenance and operations.  The Offeror’s proposal shall describe the strategy for accomplishing the implementation tasks outlined below and a timeline for the accomplishment of these tasks.  If the Offeror identifies any deficiencies in the Authority’s prospective project plan, then the deficiencies and their suggested resolution shall also be described. Similarly, if the Offeror would require additional time to implement the proposed solution, (e.g. to construct a new call center location or hire/train additional staff), these requirements shall be defined in the proposal.

    - Implementation will encompass the following tasks:

- The Selected Offeror, in coordination with the Authority, shall develop a detailed Project Plan and timeline for Mailroom implementation.  The Project Plan shall be developed in accordance with the principles of the PMBOK.

- The Selected Offeror, in coordination with the Authority, shall develop a detailed Mailroom Operations Plan, inclusive of procedural, compliance, and regulatory milestones (inspection, certification, reporting, auditing, etc.).

- The Selected Offeror, in coordination with the Authority, shall codify standard operating procedures, as well as agreed-upon benchmarks and service-level targets, in a Mailroom Standard Operating Procedures Manual.

- Implementation Deliverables.  The Selected Offeror shall provide the Authority for approval all of the following deliverables before the completion of Implementation:

- Mailroom Technology Readiness Plan.

- Verified Execution of Mailroom Technology Readiness Plan (Technology Platform).

- Fully Staffed and Operational Mailroom.

- Such other deliverables as determined by the Authority as being reasonably necessary for the completion of Implementation.

  - Reports and Project Control.

    - Regular Status Report.

During the DDI and TT Phases as described in Sections 6.1-6.3 above and the Implementation and Transition stages as described in Sections 6.5-6.6, a weekly progress report shall be provided as required by the Authority covering activities, problems and recommendations of the Selected Offeror regarding the development and implementation of the required services.  During the operation phases as described in Sections 6.4, 6.5.3 and 6.6.2, at a minimum monthly progress report relating to the maintenance of the services required by this RFP shall be provided.  During critical operational times such as but not limited to Open Enrollment periods, after solutions upgrades or major changes to operations, reports shall be provided at a higher frequency as requested by the Authority. These reports should be keyed to the work plan and timeline the Selected Offeror developed in its proposal, as amended or approved by the Authority.

    - Data Reporting Requirements.

The Selected Offeror must be able to provide reporting to the Authority as needed relating to the services rendered by the Selected Offeror sufficient to allow the Authority and PID to comply with any reporting requirements pursuant to federal or state law, regulations or sub-regulatory guidance.  In addition, the Selected Offeror shall provide pre-built reports necessary to efficiently run the operation, reports that support the monitoring of Service Level Agreements and any other measures and reports that will enable the Authority to successfully and efficiently operate.   At a minimum, the Selected Offeror must be able to report on the following data:

    - Data Reports Provided Ad Hoc

      - National Producer Number (NPN) Enrollment Report (PII) Data File – ad hoc

        - Summary: The NPN Enrollment report will contain enrollment data by agent/broker NPN code.  The report will also provide detailed enrollment data breakouts by Issuer HIOS ID and Name, Policy Status (Premium Paid or Premium Not Paid), and Registration Status of the agent/broker.

        - Represents data as of: Ad Hoc Pull Date, from beginning of OE.

        - Frequency Report Provided to the Authority: An ad hoc report provided to states as needed.

        - Business Use: To inform and support the Authority’s consumer assistance and outreach efforts, by identifying lead agents/brokers.

        - Caveats: Contains both active and cancelled policies.

      - Call Center Metrics (shared with the Authority, and not shared publicly)

        - Summary: The Call Center Metrics report will provide an overview of the types of topics asked to the call center, calls by zip code, as well as call center referrals (e.g. by an agent/broker).

        - Represents data as of: OE.

        - Frequency Report Provided to the Authority: Ad hoc.

        - Business Use: To inform and support the Authority’s understanding of consumer inquiries to the call center, by geographic location, to better support consumer assistance and outreach efforts.

        - Caveats: None.

    - Data Reports Provided during Open Enrollment

      - Weekly Open Enrollment (OE) Report (shared with the Authority, and not shared publicly)

        - Summary: The Weekly OE Report will provide specific detailed enrollment data during OE for each SBE-FP.  The report contains eligibility and plan selection data, including related financial assistance and demographic breakouts. Zip code breakouts are also provided for high-level metrics.

        - Represents data as of: As of 11/01/2017, weekly throughout OE.

        - Frequency Report Provided to the Authority: Daily as requested by the Authority but at a minimum weekly during OE, including one final report with data through end of OEP.

        - Business Use:  To inform and support the Authority’s consumer assistance and outreach efforts.

        - Caveats: Not all plan selections result in an effectuated enrollment. Specifically, some plan selections may later be canceled by the issuer, or terminated by the enrollee. Any plan selections that have already been cancelled or terminated are not included in the report.

    - Data Reports Provided Year-Round

      - Individual Enrollee Level Data File (shared with the Authority, and not shared publicly)

        - Summary: The Enrollee Primary Contact Data File provides protected information (e.g. contact information) for every active, non-canceled policy as of the pull date (for this calendar year, 09/01/2017) for each SBE-FP. Data also includes demographic information for each individual with an active policy, including gender, age, preferred language, and race/ethnicity.

        - Represents data as of: By pull date, bi-annually.

        - Frequency Report Provided to the Authority: A bi-annual report provided in the fall and spring.

        - Business Use: To inform and support the Authority’s consumer assistance and outreach efforts.

        - Caveats: One primary contact is included per policy (i.e. could be one per household of enrollees). If there was no primary contact indicated, then contact might not be provided. Policies that are canceled before the pull date are not included in this file. There may be a time lag between an issuer’s notification of a cancelation and updates to the SBE’s enrollment system, therefore, some canceled policies may still appear to be active. Sent via EFT.

      - Monthly MIDAS Plan Selection and Demographics Report (shared with the Authority, and not shared publicly)

        - Summary: The Monthly MIDAS Report provides active plan selection data for each SBE-FP. Plan selection data is provided by, for example, age, gender, race/ethnicity, metal level, language preference, need of financial assistance (APTC/CSR), consumer assistance channels, APTC amount, and plan selections by plan. The report will also include additional data on applications and application channels, new, active, and auto-reenrollments, rural/non-rural plan selections, new consumer details, dental plans, and premium/financial assistance data.  Additional metrics for auto-reenrollment details, SEP enrollments by reason, and terminations will also be included in the report. The data will also be further broken out by county and zip code.

        - Represents data as of: Beginning to end of each month.

        - Frequency Report Provided: Monthly year-round.

        - Business Use: To inform and support the Authority’s consumer assistance and outreach efforts.

        - Caveats: Some plan selections may not result in an effectuated enrollment. Some plan selections may later be canceled by the issuer or terminated by the enrollee. Any plan selections that have already been cancelled or terminated are not included in the report.

      - Effectuated Enrollment Payment Report (EEPR) (shared with the Authority, and not shared publicly)

        - Summary: The EEPR provides net monthly summary data for all effectuated enrollments of individuals who are enrolled in medical and/or dental plans by issuer and plan. The report includes effectuated enrollment member counts for APTCs and/or CSRs programs, and summary financial data for total monthly premiums, net APTC, net CSR, as well as net user fees by HIOS ID’s. The net amounts are reflective of all adjustments as of the current month’s payment cycle.

        - Represents data as of: 15th of prior month.

        - Frequency Report Provided to SBE-FPs: Monthly year-round.

        - Business Use: To inform the Authority’s understanding of the Federal Platform User Fee calculation.

        - Caveats: The data is meant to reconcile month over month. For example, the totals reported in a February coverage month for a certain HIOS ID would reconcile, or update, the January totals for that HIOS ID.  This may be done by reconciling the data in this report for the current month with the current month Preliminary Payment Report (PPR).  When reconciling with the prior month’s PPR, the Selected Offeror will need to take into account all the prior period adjustments. Please note that if the PPRs does not contain APTC or CSR amounts, the Selected Offeror will not be able to reconcile this data.  However, the Selected Offeror should be able to reconcile the user fee data. Sent via EFT.

      - Preliminary Payment Report (PPR Report) (shared with the Authority, and not shared publicly)

        - Summary: The Preliminary Payment Report (PPR Report) provides monthly data on payments issued to the issuers at both the program level (as applicable for risk corridors, reinsurance, and risk adjustment and/or any applicable manual adjustments, e.g. contraceptive user fee) and policy level.  The PPR report is only transmitted to AR, NV and NM and provides policy level details for all the policies for all the issuers within that SBE-FP. The header of the PPR indicates the net user fees the SBE-FP owes CMS.

        - Represents data as of: 15th of prior month for all effectuated policies for the current month

        - Frequency Report Provided: Monthly year-round.

        - Business Use:  To inform the Authority’s understanding of the Federal Platform User Fee calculation.

      - Account transfers sent to DHS and account transfers received from DHS

      - Details on enrollment records sent to insurance carriers

- COST SUBMITTAL

  - Cost Submittal.

The information requested in this Section 7 shall constitute the Cost Submittal.  The Cost Submittal shall be delivered electronically as a separate file and must not be included in any part of the technical submittal.  The total proposed cost should be broken down into the components set forth in Attachment A – Cost Submittal Worksheet.  Offeror should not include any assumptions in their cost submittals.  If the Offeror includes assumptions in its cost submittal, the Issuing Office may reject the proposal.  Offeror should direct in writing to the Issuing Office pursuant to Section 2.3 of this RFP any questions about whether a cost or other component is included or applies.  All Offerors will then have the benefit of the Issuing Office’s written answer so that all costs are submitted on the same basis.  Only costs associated with the base contract term will be considered for cost scoring purposes.

As noted, one of the goals of this RFP is to reduce operational costs by transitioning from reliance on the FFE to autonomous operation as an SBE.  This reduction in operational costs is essential to the operation of the reinsurance program envisioned in Act 42 of 2019, and the savings must be significant enough to fund the Commonwealth’s contribution to the operation of the reinsurance program in its entirety (see Act 42, §§ 9305(b)(4), 9503(b)(2)).

The Authority will reimburse the Selected Offeror for work satisfactorily performed after execution of a written contract and the start of the contract term, in accordance with contract requirements, and only after the Issuing Office has issued a notice to proceed.  The Authority is a Pennsylvania state-affiliated entity whose operations are funded entirely from fee-based revenue, assessed for the 2021 Plan Year at the rate of 3.0% of on-exchange premiums. This rate was established by the Authority’s originating statute and is not expected to increase over the course of this project’s timeline. For the 2020 plan year, the Authority will receive 0.5% of on-exchange premiums in a remittance from the federal government to fund transition costs. No additional funding streams, such as grant awards or Pennsylvania General Fund Appropriations, are available to fund this project.  The Authority’s revenue stream will begin in earnest in the 2021 plan year, when the entire 3.0% on-exchange premium user fee will be collected by the Authority.

The costs in the Cost Submittal (Attachment B) are the only costs that will be utilized in the scoring of the costs for this RFP.  In addition, by submitting these costs, the Offeror understands and acknowledges that payments for services will be made as follows.

Invoicing for services will be done on an annual basis for services rendered in the prior plan year with the exception of Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two.  Instead, for those costs, one quarter of the total costs for Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two may be added to the invoice for each of the plan years in phase three.  In other words, beginning January 1, 2021, the Selected Offeror may submit invoices after January 1 for: (1) the M&O Annual Costs for the prior plan year; (2) the Consumer Service Center Annual Costs for the prior plan year; and (3) one quarter of the total costs for Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two.

This will allow the Authority to spread the costs associated with Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two over four years in order to address its revenue deficiencies until the SBE is operational.

Optional contract years will also be invoiced on an annual basis for services rendered in the prior plan year.  These optional contract year costs may not exceed a 5% increase from the correlating costs in the prior plan year.

# APPENDIX A:  TRADE SECRET/CONFIDENTIAL PROPRIETARY INFORMATION NOTICE

Trade Secret/Confidential Proprietary Information Notice

may be found at the following link:

https://www.dgs.pa.gov/Documents/Procurement%20Forms/TradeSecret_ConfidentialPropertyInfoNotice.pdf

# APPENDIX B:  REQUIREMENTS FOR NON-COMMONWEALTH HOSTED APPLICATIONS / SERVICES

Requirements for Non-Commonwealth Hosted Applications/Services

The purpose of this document is to define requirements for technology solutions procured by the Commonwealth that are not hosted within Commonwealth infrastructure.

A.  Hosting Requirements

1. The Licensor or its subcontractor shall supply all hosting equipment (hardware and software) required for performance of the software and services set forth in the Quote and Statement of Work.

2. The Licensor shall provide secure access to all levels of users via the internet.

3. The Licensor shall use commercially reasonable resources and efforts to maintain adequate internet connection bandwidth and server capacity.

4. The Licensor or its subcontractors shall maintain all hosting equipment (hardware and software) and replace as necessary to maintain compliance with the Service Level Agreements.

5. The Licensor shall monitor, prevent and deter unauthorized system access. Any and all known attempts must be reported to the Commonwealth within two (2) business days.  In the event of any penetration, impermissible use or disclosure of data, loss or destruction of data, the Licensor must immediately notify the Commonwealth and take all reasonable steps to mitigate the access and to mitigate any potential harm or further disclosure, loss or destruction of data. Licensor shall comply with state and federal data breach law and shall report security incidents to the Commonwealth within one (1) hour of when the Licensor knew of such unauthorized access, use, release, or disclosure of data.

6. The Licensor or the Licensor’s subcontractor shall allow the Commonwealth or its delegate, at times chosen by the Commonwealth, to review the hosted system’s location and security architecture.

7. The Licensor’s employees or subcontractors, who are directly responsible for day-to-day monitoring and maintenance of the hosted system, and shall have industry standard certifications applicable to the environment and system architecture used.

8. The Licensor or the Licensor’s subcontractor shall locate servers in a climate-controlled environment.  The Licensor or the Licensor’s contractor shall house all servers and equipment in an operational environment that meets industry standards including climate control, fire and security hazard detection, electrical needs, and physical security.

9. The Licensor shall examine system and error logs daily to minimize and predict system problems and initiate appropriate action.

10. The Licensor shall completely test and apply patches for all third-party software products before release.  All patches shall be applied without unreasonable delay.

11. 	The Licensor shall provide the Commonwealth with its annual American Institute of Certified Public Accountants (AICPA) Attestation Standard (AT) Sec. 101 Service Organization Control (“SOC”) 2, Type 2 certification (AT Sec. 101 SOC 2, Type 2), or an equivalent certification approved by the Commonwealth.  Equivalent certifications include, but are not limited to:  International Organization of Standards (ISO) 2700x certification; certification under the Federal Information Security Management Act (FISMA); and AT Sec. 101 SOC 3 (SysTrust/WebTrust) certification.  Annually, Licensor shall provide an AT Sec. 101 SOC 2, Type 2 audit report, or its equivalent, to the Commonwealth upon request.

B.  System Availability

1. The selected Offeror shall make available the system and any custom software on a 24 x 7 basis as established by the RFP.

2. The selected Offeror shall perform routine maintenance during the planned weekly maintenance period of daily from 2 am to 5 am Easter time. Routine maintenance shall include, but is not limited to, server upgrades/patching, software upgrades/patching and hardware maintenance.

3. The selected Offeror shall perform non-routine maintenance at a mutually agreeable time with two (2) weeks advance notice to the Commonwealth.

4. From time to time, emergency maintenance may be required to bring down the system. In such situations, if possible, the selected Offeror shall give advance notice, before the system goes down for maintenance, to the Commonwealth. The selected Offeror will limit the emergency maintenance to those situations which require immediate action of bringing down the system that cannot wait for the next scheduled maintenance period.

C.  Security and Other Requirements

1. The Licensor shall conduct a third-party independent security/vulnerability assessment prior to implementation at its own expense and submit the results of such assessment to the Commonwealth within forty-five (45) business days prior to the implementation date.  After the implementation date, on an annual basis the Licensor shall conduct a third-party independent security/vulnerability assessment at its own expense and submit the results of such assessment to the Commonwealth within three (3) business days of completion of the assessment.

2. The Licensor shall comply with the Commonwealth’s directions/resolutions to remediate the results of the security/vulnerability assessment to align with the standards of the Commonwealth.

3. The Licensor shall use industry best practices to protect access to the system with a firewall and firewall rules to prevent access by non-authorized users and block all improper and unauthorized access attempts.

4. The Licensor shall use industry best practices to provide system intrusion detection and prevention in order to detect intrusions in a timely manner.

5. The Licensor shall use industry best practices to provide malware and virus protection on all servers and network components.

6. The Licensor shall limit access to the system and servers and provide access only to those staff that must have access to provide services proposed.

7. The Licensor shall provide all Services, using security technologies and techniques in accordance with industry best practices and the Commonwealth’s ITPs set forth in Attachment 1, including those relating to security policies, procedures, and requirements, the prevention and detection of fraud and any other inappropriate use or access of systems and networks.

8.   Attachment 2, which is hereby made a part of this Agreement, is a Business Associate Agreement with which the Licensor must agree if the services require it.  If the Business Associate Agreement or other privacy and security requirements are applicable, the Commonwealth agency or agencies procuring from or using services of the Licensor will complete and submit Attachment 3, which is hereby made a part of this Agreement.

D.  Data Storage

1. The Licensor shall use industry best practices to update and patch all systems and third-party software to reduce security risk. The Licensor shall protect their systems with anti-virus, host intrusion protection, incident response monitoring and reporting, network firewalls, application firewalls, and employ system and application patch management to protect its network and customer data from unauthorized disclosure.

2. The Licensor shall be solely responsible for all data storage required.

3. The Licensor shall take all necessary measures to protect the data including, but not limited to, the backup of the servers on a daily basis in accordance with industry best practices and encryption techniques.

4.  The Licensor agrees to have appropriate controls in place to protect critical or sensitive data and shall employ stringent policies, procedures, and best practices to protect that data particularly in instances where sensitive data may be stored on a Licensor-controlled or Licensor-owned electronic device.

5.  The Licensor shall utilize a secured backup solution to prevent loss of data, back up all data every day and store backup media. Storage of backup media offsite is required.  Stored media must be kept in an all-hazards protective storage safe at the worksite and when taken offsite. All back up data and media shall be encrypted.

E.  Disaster Recovery

1. The selected Offeror shall employ reasonable disaster recovery procedures to assist in preventing interruption in the use of the system.

F.  Adherence to Policy

Licensor support and problem resolution solution shall provide a means to classify problems as to criticality and impact and with appropriate resolution procedures and escalation process for each classification of problem.

Licensor shall abide by all the Commonwealth’s policies (Information Technology Polices (ITPs)).

Licensor shall comply with all pertinent federal and state privacy regulations.

H.  Closeout

1. When the contract term expires or terminates, and at any other time at the written request of the Commonwealth; the selected Offeror must promptly return to the Commonwealth all its data (and all copies of this information), in a format agreed to by the Commonwealth.

# APPENDIX C:  INFORMATION TECHNOLOGY POLICIES

Information Technology Policies (ITPs) for  Outsourced/Licensor(s)-hosted Solutions

| ITP Number | Title | Type |
| --- | --- | --- |
| ACC001 | IT Accessibility Policy | Policy |
| INF001 | Database Management Systems | Policy |
| INF003 | Data Modeling Standards | Policy |
| INFRM006 | Electronic Documents Management Systems | Policy |
| PRV001 | Commonwealth of Pennsylvania Electronic Information Privacy Policy | Policy |
| SEC001 | Enterprise Host Security Software Suite Standards and Policy | Policy |
| SEC004 | Enterprise Web Application Firewall | Policy |
| SEC005 | Commonwealth Application Certification and Accreditation | Policy |
| SEC007 | Minimum Standards for User IDSs and Passwords | Policy |
| SEC010 | Virtual Private Networks Standards | Policy |
| SEC011 | Enterprise Policy and Software Standards for Agency Firewalls | Policy |
| SEC019 | Policy and Procedures for Protecting Commonwealth Electronic Data | Policy |
| SEC020 | Encryption Standards for Data at Rest | Policy |
| SEC024 | IT Security Incident Reporting Policy | Policy |
| SEC025 | Proper Use and Disclosure of Personally Identifiable Information (PII) | Policy |
| SEC031 | Encryption Standards for Data in Transit | Policy |
| SEC034 | Enterprise Firewall Rule Set | Policy |
| SFT006 | Internet Browser Policy | Policy |
| SFT007 | Office Productivity Software Policy | Policy |
| SYM003 | Off-site Storage for Commonwealth Agencies | Policy |
| SYM006 | Commonwealth IT Resources Patching Policy | Policy |

# APPENDIX D:  REQUIRED INTERFACES & SYSTEMS INTEGRATION

| Interface Name | Data Source | Short Description | Incoming / Outgoing (from PA) | Frequency |
| --- | --- | --- | --- | --- |
| Account Transfer | Outbound to DHS* Inbound to SBE | Transfer the individual’s application and all relevant verification data obtained by the SBE to the Medicaid or CHIP agency, and vice versa. | Incoming and Outgoing | Real-time (24/7) |
| Non-ESI MEC | DHS Client Information System | Obtain Medicaid, and CHIP eligibility details based on SSN. | Outgoing | Real-time (24/7) |

Interfaces with DHS for Medicaid and CHIP

- The following information is assumed by DHS to be verified when an account transfer is sent from the SBE

  - Citizenship

  - Eligible Immigration Status

  - Annual Income

  - Incarceration Status

Employer Sponsored Insurance (ESI) minimum essential coverage (MEC)

| Interface Name | Data Source | Short Description | Incoming / Outgoing (from PA) | Frequency | CMS Version (used by PA) |
| --- | --- | --- | --- | --- | --- |
| RIDP (Remote Identity Proofing) | FDSH | Obtain data from Experian to perform remote identity proofing to validate a user claim that he/she is who he/she claims to be. | Outgoing | Real-time (24/7) | V2.0 |
| SSA (Social Security Administration) – Composite | FDSH | Obtain data regarding SSN, citizenship, and other types of SSA data for the individual. | Outgoing | Real-time (24/7) | V1.0 |
| VLP (Verify Lawful Presence) from Department of Homeland Security | FDSH | Obtain data regarding an individual’s lawful presence with DHS using DHS existing web services. | Outgoing | Real-time (24/7) | V37.0 |
| TALX-FDSH (The Employment and Income Verification System) | FDSH | Obtain employer and income information from Equifax. | Outgoing | Real-time (24/7) | V1.0 |
| RRV (Renewal & Redetermination Verification) | FDSH - TALX, FDSH - SSA | Leverage CMS Bulk Service (H79 RRV) to obtain verification data from FDSH during automated renewal processing | Request / Response | Batch (Monthly) | V1.0 |

FDSH Interfaces used by DHS

Insurance Carriers

- ANSI 834 enrollment transactions

- ANSI 820 premium transactions

- ANSI 835 payment transactions

Required Systems Integration with Commonwealth Systems:

- Keystone Login to register and Authenticate citizens accounts

- Keystone Login to authenticate Authority and other Commonwealth agency users

- Commonwealth Active Directory to authenticate business partner users

# APPENDIX E:  STANDARD TERMS & CONDITIONS

Commonwealth of Pennsylvania Standard Terms and Conditions

The Terms and Conditions governing this procurement and eventual contract can be found at:

https://www.dgs.pa.gov/Documents/Procurement2520Forms/IT_Terms_and_Conditions.docx&sa=U&ved=2ahUKEwjB4KvHzIDkAhVOU98KHYzLCBcQFjAAegQIABAB&usg=AOvVaw2evDe03iOksIx0m3L4lnNZ

# APPENDIX F:  CUSTOMER SERVICE TRANSFORMATION STANDARDS

The Commonwealth is committed to improving digital interactions with citizens as well as individuals and entities that conduct business with or on behalf of the Commonwealth (each a “Business Partner”).  Customer Service Transformation was launched to help the Commonwealth achieve these objectives and is based on the following six design principles:

- A single online destination for services;

- Secure access to services through a single login;

- Consistent and user-friendly online experience across all services;

- A consolidated and streamlined digital footprint;

- Continuous improvement through customer feedback; and

- A single phone number to direct citizens or Business Partners to the services they are seeking.

Offerors are expected to acknowledge these principles.  The selected Offeror shall align their performance and deliverables under the contract awarded from this RFP with these principles.

The following section provides more information about the design principles.

Design Principles and Requirements:

- Keystone Login provides: - A single online destination for services:

A single online destination will enable citizens and Business Partners to locate services and conduct business in the Commonwealth, even if they do not know which agency to contact. Citizens and Business Partners can still navigate directly to services on agency websites, if they wish.

Offerors must be able to integrate with the single online destination, starting with PA.GOV. The selected Offeror shall be able to receive and validate the credentials of a citizen or Business Partner that were previously authenticated from an active session. This process is further defined below in design principle 2 - secure access to services through a single login.

- Secure access to services through a single login:

The Commonwealth implemented a single login system known as Keystone Login. The purpose of Keystone Login is to provide a consistent and secure approach to account administration. The Keystone Login offers citizens and Business Partners a single online point of access to services offered by multiple Commonwealth agencies or other Business Partners. It is critical that by using Keystone Login any citizen or Business Partner can work with any Commonwealth agency or other Business Partner through the Commonwealth’s external facing applications using a single login credential. The consistent and modern authentication standards available through Keystone Login will increase convenience for citizens and Business Partners by simplifying account management and eliminating the need to remember multiple usernames and passwords, while also strengthening the Commonwealth’s security posture.

In addition, Keystone Login provides the ability for a citizen or Business Partner to create a single profile managed by Keystone Login. The selected Offeror shall register with and utilize the Commonwealth’s Keystone Login. Applications that utilize Keystone Login can leverage authentication methods through one of the following approaches; (1) via a series of Application Programming Interfaces (“APIs”), or (2) as a redirect to the Keystone Login Portal. A detailed Developer Integration Guide will be provided to the selected Offeror, however, to aid in determining the level of effort, a summary version of the Developer Integration Guide and the Keystone Login Branding Guidelines are available at the following location: http://keystonelogindevelopers.pa.gov. The summary version of the Developer Integration Guide and the Keystone Login Branding Guidelines should be reviewed by the Offerors prior to responding to this RFP to ensure the Offerors understand the mandatory APIs and services to be made available to citizens and Business Partners. The Offerors shall include in their proposals an acknowledgement that they will utilize the Keystone Login. If the Offeror requires any additional information to verify the identification of citizens or Business Partners through the authentication process provided by Keystone Login, the Offeror must identify the additional required information in its proposal. - If the selected Offeror will be responsible for helpdesk calls from application users, Offeror shall comply with the following: The selected Offeror is expected to provide Tier 1 Helpdesk support. Keystone Login provides an internal admin dashboard designed to provide Helpdesk information to aid a caller with several Tier 1 level tasks. This is a secure internal administration site; hence, the selected Offeror will need a COPA account, along with VPN in order to access this site and be provided access by the Commonwealth. The dashboard provides the following information: Exception Logs: A log of all the errors that occur in the Keystone Login site, calls to Keystone Login APIs, and the Admin site. The list can be searched and filtered by different parameters (User Name, Email Address, Start Date, End Date, Agency, or Application). Returns: ID, Log Date, User Name, User Email, Application Code, Message, Method, File Path, Line Number and Stack Trace. User Logs: A log of all user activity. The list can be searched and filtered by different parameters (User Name, Email Address, Start Date, End Date, Agency, or Application). Returns: ID, Log Date, User Name, User Email, Application Code, User Event Type and Message. Search: Used for searching users in Commonwealth domains. Search also provides the ability to edit Keystone Login accounts, unlock accounts when locked, change or reset passwords. User Search: Username, Email address, first name, last name, phone or domain. Returns: Name, User Name, Domain with buttons to see Details, User Logs, Exception Logs, Reset Password, Change Password, Edit, or Social Logins.

- A consistent and user-friendly online experience across all services:

A common look and feel increases trust by enabling citizens and Business Partners to easily recognize official services provided by the Commonwealth. This also includes ensuring that online services and information are accessible to all citizens and Business Partners, regardless of ability. Offerors shall acknowledge compliance with the Commonwealth’s web site and mobile application design standards. Refer to the Commonwealth Information Technology Policies (ITPs) SFT002 – Commonwealth of PA Website Standards, NET005 - Commonwealth External and Internal Domain Name Services (DNS), and SFT009 – Application Development. Offerors must acknowledge and demonstrate compliance to relevant federal, state and local laws, regulations, rules and legislation, including, but not limited to: - Title III of the Americans with Disabilities Act (ADA) which prohibits discrimination on the basis of disability; - Section 508 Amendment to the Rehabilitation Act of 1973 which requires all Federal agencies' electronic and information technology to be accessible to those with disabilities; and - Section 504 of the Rehabilitation Act which prohibits discrimination on the basis of disability for entities receiving federal funds. In addition, Offerors must acknowledge compliance with the Web Content Accessibility Guidelines (WCAG) 2.0, which are industry standards. The selected Offeror must provide quarterly reports that demonstrate compliance with WCAG. Refer to the Commonwealth Information Technology Policy (ITP) ACC001 – Information Technology Accessibility Policy for additional information.

- A consolidated and streamlined digital footprint:

The Commonwealth is looking to streamline its online presence and make information easier to find by eliminating or consolidating small, outdated or low traffic Commonwealth websites. The selected Offerors must use the PA.GOV domain for proposed websites. By using PA.GOV, citizens and Business Partners will know that they are utilizing official services from the Commonwealth.

- Continuous improvement through customer feedback:

The Commonwealth will be collecting feedback from our citizen and Business Partners regarding the Customer Service Transformation. The Commonwealth may use the feedback to identify new opportunities to improve and innovate services. The selected Offerors shall have the ability to collect satisfaction and feedback related data from citizens and Business Partners.

- A single phone number to direct citizens to the services they are seeking:

The Commonwealth intends to make it easier for citizens and Business Partners to find the services they are seeking by calling a single Commonwealth phone number. Citizens and Business Partners may still contact agencies directly through existing call centers and phone numbers, if they wish. The selected Offeror will be expected to collaborate with this initiative where appropriate.

# ATTACHMENT A:  PROPOSAL COVER SHEET

PROPOSAL COVER SHEET

COMMONWEALTH OF PENNSYLVANIA

Pennsylvania Insurance Department

on behalf of the Pennsylvania Health Insurance Exchange Authority

RFP #6100048766

The Proposal of the Offeror identified below for the above-referenced RFP is submitted electronically, and is comprised of separate files for the Technical Submittal and the Cost Submittal:

| Contractor Information: |  |  |
| --- | --- | --- |
| Contractor Name |  |  |
| Contractor Mailing Address |  |  |
| Contractor Website |  |  |
| Contractor Contact Person |  |  |
| Contact Person’s Phone Number |  |  |
| Contact Person’s Facsimile Number |  |  |
| Contact Person’s E-Mail Address |  |  |
| Contractor Federal ID Number |  |  |
| Contractor SAP/SRM Vendor Number |  |  |
| Submittals Enclosed and Separately Sealed: |  |  |
|  | Technical Submittal |  |
|  | Cost Submittal |  |

_________________________________________	___________________________________

Printed Name and Title					Date

__________________________________________

Signature of an official authorized to bind the Offeror to the provisions contained in the Offeror’s Proposal

# ATTACHMENT B:  COST SUBMITTAL FORM

COST SUBMITTAL FORM

Technology Platform and Consumer Assistance Center for the Pennsylvania Health Insurance Exchange

RFP #6100048766

BASE CONTRACT COSTS

|  | COST |
| --- | --- |
| Technology Platform Costs |  |
| Phase One – DDI | $ |
| Phase Two - TT | $ |
| Phase Three – M&O Annual Costs for Plan Year 2021 | $ |
| Phase Three – M&O Annual Costs for Plan Year 2022 | $ |
| Phase Three – M&O Annual Costs for Plan Year 2023 | $ |
| Phase Three – M&O Annual Costs for Plan Year 2024 | $ |
| TOTAL TECNOLOGY PLATFORM COST FOR BASE CONTRACT | $ |
| Consumer Assistance Center Costs |  |
| Phase One – Implementation | $ |
| Phase Two - Transition | $ |
| Phase Three – Consumer Assistance Center Annual Costs for Plan Year 2021 | $ |
| Phase Three – Consumer Assistance Center Annual Costs for Plan Year 2022 | $ |
| Phase Three – Consumer Assistance Center Annual Costs for Plan Year 2023 | $ |
| Phase Three – Consumer Assistance Center Annual Costs for Plan Year 2024 | $ |
| TOTAL CONSUMER ASSISTANCE CENTER COST FOR BASE CONTRACT | $ |
| GRAND TOTAL ALL COSTS FOR BASE CONTRACT | $ |

The costs in the chart above are the only costs that will be utilized in the scoring of the costs for this RFP.  In addition, by submitting these costs, the Offeror understands that payments will be made as follows.

Invoicing for services will be done on an annual basis for services rendered in the prior plan year with the exception of Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two.  Instead, for those costs, one quarter of the total costs for Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two may be added to the invoice for each of the plan years in phase three.  In other words, beginning on January 1, 2021, the Selected Offeror may submit invoices after January 1 for: (1) the M&O Annual Costs for the prior plan year; (2) the Consumer Service Center Annual Costs for the prior plan year; and (3) one quarter of the total costs for Technology Platform Phases One and Two and Consumer Assistance Center Phases One and Two.

OPTIONAL CONTRACT YEAR COSTS

The costs below are for optional contract years for Plan Years 2025 through and including 2029.  These costs may not exceed a 5% increase from the correlating costs in the prior plan year.

|  | COST |
| --- | --- |
| Technology Platform Costs |  |
| M&O Annual Cost for Optional Plan Year 2025 | $ |
| M&O Annual Cost for Optional Plan Year 2026 | $ |
| M&O Annual Cost for Optional Plan Year 2027 | $ |
| M&O Annual Cost for Optional Plan Year 2028 | $ |
| M&O Annual Cost for Optional Plan Year 2029 | $ |
| Consumer Assistance Center Costs |  |
| Consumer Assistance Center Plan Year 2025 | $ |
| Consumer Assistance Center Plan Year 2026 | $ |
| Consumer Assistance Center Plan Year 2027 | $ |
| Consumer Assistance Center Plan Year 2028 | $ |
| Consumer Assistance Center Plan Year 2029 | $ |

Invoicing for services will be done on an annual basis for services rendered in the prior year.

# ATTACHMENT C:  BUSINESS ASSOCIATE AGREEMENT

COMMONWEALTH OF PENNSYLVANIA

SAMPLE BUSINESS ASSOCIATE AGREEMENT

WHEREAS, the __________________ (Covered Entity) and _________________________ (Business Associate) intend to protect the privacy and security of certain Protected Health Information (PHI) to which Business Associate may have access in order to provide goods or services to or on behalf of Covered Entity, in accordance with the Health Insurance Portability and Accountability Act of 1996, as amended, Pub. L. No. 104-191 (HIPAA), the Health Information Technology for Economic and Clinical Health (HITECH) Act, as amended, Title XIII of Division A and Title IV of Division B of the American Recovery and Reinvestment Act of 2009 (ARRA), as amended, Pub. L. No. 111-5 (Feb. 17, 2009) and related regulations, the HIPAA Privacy Rule (Privacy Rule), 45 C.F.R. Parts 160 and 164, as amended, the HIPAA Security Rule (Security Rule), 45 C.F.R. Parts 160, 162 and 164), as amended, 42 C.F.R. §§ 431.301-431.302, 42 C.F.R. Part 2, 45 C.F.R. § 205.50, 42 U.S.C. § 602(a)(1)(A)(iv), 42 U.S.C. § 1396a(a)(7), 35 P.S. § 7607, 50 Pa. C.S. § 7111, 71 P.S. § 1690.108(c), 62 P.S. § 404, 55 Pa. Code Chapter 105, 55 Pa. Code Chapter 5100, the Pennsylvania Breach of Personal Information Notification Act, Act of December 22, 2005, P.L. 474, No. 94,as amended, 73 P.S. §§ 2301—2329, and other relevant laws, including subsequently adopted provisions applicable to use and disclosure of confidential information, and applicable agency guidance; and,

WHEREAS, Business Associate may receive PHI from Covered Entity, or may create or obtain PHI from other parties for use on behalf of Covered Entity, which PHI may be used or disclosed only in accordance with this Agreement and the standards established by applicable laws and agency guidance; and

WHEREAS, Business Associate may receive PHI from Covered Entity, or may create or obtain PHI from other parties for use on behalf of Covered Entity, which PHI must be handled in accordance with this Agreement and the standards established by HIPAA, the HITECH Act and related regulations, the Privacy Rule, the Security Rule and other applicable laws and agency guidance.

NOW, THEREFORE, Covered Entity and Business Associate agree as follows:

- Definitions.

  - “Business Associate” shall have the meaning given to such term under HIPAA, the HITECH Act and related regulations, the Privacy Rule, the Security Rule and agency guidance.

  - “Covered Entity” shall have the meaning given to such term under HIPAA, the HITECH Act and related regulations, the Privacy Rule, the Security Rule and agency guidance.

  - “HIPAA” shall mean the Health Insurance Portability and Accountability Act of 1996, as amended, Pub. L. No. 104-191.

  - “HITECH Act” shall mean the Health Information Technology for Economic and Clinical Health (HITECH) Act, as amended, Title XIII of Division A and Title IV of Division B of the American Recovery and Reinvestment Act of 2009 (ARRA), Pub. L. No. 111-5 (Feb. 17, 2009).

  - “Privacy Rule” shall mean the standards for privacy of individually identifiable health information in 45 C.F.R. Parts 160 and 164, as amended, and related agency guidance.

  - “Protected Health Information” or “PHI” shall have the meaning given to such term under HIPAA, the HITECH Act and related regulations, the Privacy Rule, the Security Rule (all as amended) and agency guidance.

  - “Security Rule” shall mean the security standards in 45 C.F.R. Parts 160, 162 and 164, as amended, and related agency guidance.

  - “Unsecured PHI” shall mean PHI that is not secured through the use of a technology or methodology as specified in HITECH Act regulations, as amended, and agency guidance or as otherwise defined in the HITECH Act, as amended.

- Stated Purposes for Which Business Associate May Use or Disclose PHI.  The Parties hereby agree that Business Associate shall be permitted to use and/or disclose PHI provided by or obtained on behalf of Covered Entity for the following stated purposes, except as otherwise stated in this Agreement:

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

NO OTHER DISCLOSURES OF PHI OR OTHER INFORMATION ARE PERMITTED.

- BUSINESS ASSOCIATE OBLIGATIONS:

  - Limits on Use and Further Disclosure.  Business Associate shall not further use or disclose PHI provided by, or created or obtained on behalf of Covered Entity other than as permitted or required by this Addendum, as requested by Covered Entity, or as required by law and agency guidance.

  - Appropriate Safeguards.  Business Associate shall establish and maintain appropriate safeguards to prevent any use or disclosure of PHI other than as provided for by this Agreement.  Appropriate safeguards shall include implementing administrative, physical and technical safeguards that reasonably and appropriately protect the confidentiality, integrity and availability of the electronic PHI that is created, received, maintained or transmitted on behalf of the Covered Entity and limiting use and disclosure to applicable minimum necessary requirements as set forth in applicable federal and state statutory and regulatory requirements and agency guidance.

  - Reports of Improper Use or Disclosure.  Business Associate hereby agrees that it shall report to ________________at ____________, within two (2) days of discovery any use or disclosure of PHI not provided for or allowed by this Agreement.

  - Reports on Security Incidents.  In addition to following the breach notification requirements in section 13402 of the Health Information Technology for Economic and Clinical Health Act of 2009 (“HITECH Act”), as amended, and related regulations, the Privacy Rule, the Security Rule, agency guidance and other applicable federal and state laws, Business Associate shall report to _______________at ____________, within two (2) days of discovery any security incident of which it becomes aware.  At the sole expense of Business Associate, Business Associate shall comply with all federal and state breach notification requirements, including those applicable to Business Associate and those applicable to Covered Entity.  Business Associate shall indemnify the Covered Entity for costs associated with any incident involving the acquisition, access, use or disclosure of Unsecured PHI in a manner not permitted under federal or state law and agency guidance.  For purposes of the security incident reporting requirement, inconsequential unsuccessful incidents that occur on a daily basis, such as scans, “pings,” or other unsuccessful attempts to penetrate computer networks or servers containing electronic PHI maintained by Business Associate, need not be reported in accordance with this section, but may instead be reported in the aggregate on a monthly basis.

  - Subcontractors and Agents.  At any time PHI is provided or made available to Business Associate subcontractors or agents, Business Associate shall provide only the minimum necessary PHI for the purpose of the covered transaction and shall first enter into a subcontract or contract with the subcontractor or agent that contains substantially the same terms, conditions and restrictions on the use and disclosure of PHI as contained in this Agreement.

  - Right of Access to PHI.  Business Associate shall allow, for any PHI maintained in a designated record set, Covered Entity to have access to and copy an individual’s PHI within five (5) business days of receiving a written request from the Covered Entity.  Business Associate shall provide PHI in the format requested, if it is readily producible in such form and format; or if not, in a readable hard copy form or such other form and format as agreed to by Business Associate and the individual.  If the request is for information maintained in one or more designated record sets electronically and if the individual requests an electronic copy of such information, Business Associate must provide Covered Entity with access to the PHI in the electronic form and format requested by the individual, if it is readily producible in such form and format; or, if not, in a readable electronic form and format as agreed to by the Business Associate and Covered Entity.  If any individual requests from Business Associate or its agents or subcontractors access to PHI, Business Associate shall notify Covered Entity within five (5) business days.  Business Associate shall further conform with all of the requirements of 45 C.F.R. § 164.524 and other applicable laws, including the HITECH Act, as amended, related regulations and agency guidance.  Business Associate shall indemnify Covered Entity for costs/damages associated with Business Associate’s failure to respond within the time frames set forth in this Section 3(f).

  - Amendment and Incorporation of Amendments.  Within five (5) business days of receiving a written request from Covered Entity for an amendment of PHI maintained in a designated record set, Business Associate shall make the PHI available and incorporate the amendment to enable Covered Entity to comply with 45 C.F.R. § 164.526, applicable federal and state law, including the HITECH Act , as amended and related regulations, the Privacy Rule, the Security Rule and agency guidance.  If any individual requests an amendment from Business Associate or its agents or subcontractors, Business Associate shall notify Covered Entity within five (5) business days.

  - Provide Accounting of Disclosures.  Business Associate shall maintain a record of all disclosures of PHI made by Business Associate which are not excepted from disclosure accounting requirements under HIPAA, HITECH and related regulations, the Privacy Rule or the Security Rule (all as amended) in accordance with 45 C.F.R. § 164.528 and other applicable laws and agency guidance, including the HITECH Act and related regulations.  Such records shall include, for each disclosure, the date of the disclosure, the name and address of the recipient of the PHI, a description of the PHI disclosed, the name of the individual who is the subject of the PHI disclosed, and the purpose of the disclosure.  Business Associate shall make such record available to the Covered Entity within five (5) business days of a written request for an accounting of disclosures.  Business Associate shall indemnify Covered Entity for costs/damages associated with Business Associate’s failure to respond within the time frames set forth in this Section 3(h).

  - Requests for Restriction.  Business Associate shall comply with requests for restrictions on disclosures of PHI about an individual if the disclosure is to a health plan for purposes of carrying out payment or health care operations (and is not for treatment purposes), and the PHI pertains solely to a health care item or service for which the service involved was paid in full out-of-pocket.  For other requests for restriction, Business associate shall otherwise comply with the Privacy Rule, as amended, and other applicable statutory and regulatory requirements and agency guidance.

  - Access to Books and Records.  Business Associate shall make its internal practices, books and records relating to the use or disclosure of PHI received from, or created or received by Business Associate on behalf of the Covered Entity, available to the Secretary of Health and Human Services or designee for purposes of determining compliance with applicable laws and agency guidance.

  - Return or Destruction of PHI.  At termination of this Agreement, Business Associate hereby agrees to return or destroy all PHI provided by or obtained on behalf of Covered Entity.  Business Associate agrees not to retain any copies of the PHI after termination of this Agreement.  If return or destruction of the PHI is not feasible, Business Associate agrees to extend the protections of this Agreement to limit any further use or disclosure until such time as the PHI may be returned or destroyed.  If Business Associate elects to destroy the PHI, it shall certify to Covered Entity that the PHI has been destroyed.

  - Maintenance of PHI.  Notwithstanding Section 3(k) of this Agreement, Business Associate and its subcontractors or agents shall retain all PHI throughout the term of the Agreement and shall continue to maintain the information required under the various documentation requirements of this Agreement (such as those in Section 3(h)) for a period of six (6) years after termination of the Agreement, unless Covered Entity and Business Associate agree otherwise.

  - Mitigation Procedures.  Business Associate agrees to establish and to provide to Covered Entity upon request, procedures for mitigating, to the maximum extent practicable, any harmful effect from the use or disclosure of PHI in a manner contrary to this Agreement or the Privacy Rule, as amended.  Business Associate further agrees to mitigate any harmful effect that is known to Business Associate of a use or disclosure of PHI by Business Associate in violation of this Agreement or applicable laws and agency guidance.

  - Sanction Procedures.  Business Associate agrees that it shall develop and implement a system of sanctions for any employee, subcontractor or agent who violates this Agreement, applicable laws or agency guidance.

  - Grounds for Breach.  Non-compliance by Business Associate with this Agreement or the Privacy or Security Rules, as amended, is a breach of the Agreement, if Business Associate knew or reasonably should have known of such non-compliance and failed to immediately take reasonable steps to cure the non-compliance.  Commonwealth may elect to terminate Business Associate’s contract for such breach.

  - Termination by Commonwealth.  Business Associate authorizes termination of this Agreement by the Commonwealth if the Commonwealth determines, in its sole discretion, that the Business Associate has violated a material term of this Agreement.

  - Failure to Perform Obligations.  In the event Business Associate fails to perform its obligations under this Agreement, Covered Entity may immediately discontinue providing PHI to Business Associate.  Covered Entity may also, at its option, require Business Associate to submit to a plan of compliance, including monitoring by Covered Entity and reporting by Business Associate, as Covered Entity in its sole discretion determines to be necessary to maintain compliance with this Agreement and applicable laws and agency guidance.

  - Privacy Practices.  Covered Entity will provide Business Associate with all applicable forms, including but not limited to, any form used for Notice of Privacy Practices, Accounting for Disclosures, or Authorization, upon the effective date designated by the Program or Covered Entity.  Covered Entity may change applicable privacy practices, documents and forms.  The Business Associate shall make reasonable endeavors to implement changes as soon as practicable, but not later than 45 days from the date of notice of the change.  Business Associate shall otherwise comply with all applicable laws and agency guidance pertaining to notices of privacy practices, including the requirements set forth in 45 C.F.R. § 164.520.

- Obligations of Covered Entity:

  - Provision of Notice of Privacy Practices.  Covered Entity shall provide Business Associate with the notice of privacy practices that the Covered Entity produces in accordance with applicable law and agency guidance, as well as changes to such notice.  Covered Entity will post on its website any material changes to its notice of privacy practices by the effective date of the material change.

  - Permissions.  Covered Entity shall provide Business Associate with any changes in, or revocation of, permission by individual to use or disclose PHI of which Covered Entity is aware, if such changes affect Business Associate’s permitted or required uses and disclosures.

  - Restrictions.  Covered Entity shall notify Business Associate in writing of any restriction to the use or disclosure of PHI that the Covered Entity has agreed to in accordance with 45 C.F.R. § 164.522, as amended, and other applicable laws and applicable agency guidance, to the extent that such restriction may affect Business Associate’s use or disclosure of PHI.

  - Requests.  Covered Entity shall not request Business Associate to use or disclose PHI in any manner that would not be permissible under HIPAA, HITECH and related regulations, the Privacy Rule or the Security Rule, all as amended, if done by Covered Entity.

- MISCELLANEOUS:

  - Regulatory References.  A reference in this Addendum to a section in HIPAA, HITECH and related regulations, the Privacy Rule or the Security Rule refers to the most current version of the section in effect or as amended.

  - Amendment.  The parties agree to take such action as is necessary to amend this Addendum from time to time in order to ensure compliance with the requirements of the HIPAA, HITECH and related regulations, the Privacy Rule, the Security Rule and any other applicable law, all as amended.

  - Conflicts.  In the event that any terms of this Agreement are inconsistent with the terms of the Agreement, then the terms of this Agreement shall control.

# ATTACHMENT D:  SIGN-OFF DOCUMENT

Sign-Off Document No. ____, under Agreement No. __________

Between

[Licensor____________________]. and the Commonwealth of PA, [Agency]

[Licensor____________________] Agency-level Deployment

This document becomes, upon its execution by the signatories named below, a legally valid, binding part of Software/Services License Requirements Agreement No. _________ between the Commonwealth and ______(Licensor), and is subject to the terms of that Agreement.

- Scope of Deployment (need not be entire agency):

- Nature of Data implicated or potentially implicated:

- Agency Policies to which Licensor. is subject (incorporated by reference):

- Background checks (describe if necessary):

- Additional requirements (describe with specificity):

- Is Licensor. a Business Associate (yes or no)?

If yes, the attached Business Associates Agreement, as completed by the Agency, is applicable and is hereby incorporated into this Sign-Off Document by reference.

Agency Contact Person signature and Date: 	___________________________________

[Licensor____________________]

Authorized Signatory and Date:  	_______________________________________________

# ATTACHMENT E:  CLOUD USE CASE QUESTIONNAIRE

# This questionnaire is required to be completed if the Offeror is going to host the solution with a Cloud service provider.

Cloud Use Case Questionnaire

- System Monitoring / Audit Logging

- Commonwealth will need access to application / administrative audit logs.

Supplier Response:

{insert response}

- What level of verbosity will be logged for administrative and user activity, specifically around vital record modifications / creation / deletion?

Supplier Response:

{insert response}

- Can the Offeror provide a sample copy of the logs so the Commonwealth can see the level of detail that is captured?

Supplier Response:

{insert response}

- How can Commonwealth staff gain access to specific log data for review?

Supplier Response:

{insert response}

- Can reports be established within a customer administrative portal?

Supplier Response:

- What logging tool does the Offeror use?  Splunk?  Is there a dashboard capability to view unusual activities?

Supplier Response:

{insert response}

- What protections does the Offeror propose to protect inappropriate access to the database from internal users? Specifically, any Offeror employees that may have administrative rights.

Supplier Response:

{insert response}

B.  Hosting Locations and Impact of Outage

- Confirm applicable FedRamp level (high or moderate level) is achieved. The FedRamp is required for the infrastructure and the application.

Supplier Response:

{insert response}

- Confirm hosting locations are in the US (primary, backup, failover, etc.).

Supplier Response:

{insert response}

- Confirm the system will be setup as High Availability using multiple regions or SLAs will apply to address business impact.

Supplier Response:

{insert response}

- Incident Notification

- The Offeror must acknowledge they are responsible for a data breach.

Supplier Response:

{insert response}

- Confirm Offeror has agreed to data breach notification timeframes that are within the COPA ITPs – Note the Commonwealth policy is outlined in ITP-024; reporting the incident within thirty (30) minutes for critical/high or one (1) hour of detection for medium is required for Protected Information (ITP-SEC019)

Supplier Response:

{insert response}

- Vulnerability Scanning

- How often does the Offeror perform vulnerability scanning (both authenticated and non-authenticated scans)?

Offeror Response:

{insert response}

- The scan results need to be shared with Commonwealth staff.

Offeror Response:

{insert response}

- User Authentication

- Confirm the SaaS solution supports ADFS integration for user authentication.

Offeror Response:

{insert response}

- Confirm the application will not require proxy bypass?  This refers to Commonwealth users using the application.  Since the application is cloud based the security team wants to make sure the access is set up properly instead of just bypassing all firewalls.

Offeror Response:

{insert response}

- How will non-Commonwealth users access the application?  Keystone Login/user is preferred – this requirement would need a change order to implement.

Offeror Response:

{insert response}

- How are new users registered to use the application?

Offeror Response:

{insert response}

- Does the application delegate administrative authority?

Offeror Response:

{insert response}

# ATTACHMENT F: DRAFT SERVICE LEVEL AGREEMENTS AND ASSOCIATED LIQUIDATED DAMAGES

Draft Service Level Agreements and Associated Liquidated Damages – IT Maintenance and Operations

Contractor shall meet or exceed the following Service Level Agreements (SLA), as measured by the Key Performance Indicators. Beginning in the third month after Go-Live, if Contractor fails to meet the KPIs as described below, and Contractor’s failure is not attributable to the Authority or a third party, Contractor shall owe the Authority the amount of the associated Liquidated Damages, which shall be credited to the associated invoice for the period of time in which the SLA deviation occurred. The process for reporting and monitoring SLA shall be mutually defined by the Selected Offeror and the Authority during the contracting process.

The parties shall confirm compliance (or failure) within ten (10) business days from the end of the measurement period, unless the Authority has approved another date after request by the Contractor.  The Authority will invoice the Contractor for the applicable amount of liquidated damages.

| 1. Service Level Agreement – System Availability |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| System availability is to be defined as the percentage uptime in a month that the Individual Exchange environments (including all associated components) are available to users or to perform in a back- up capacity, including all weekends and holidays. Negotiated downtime for system maintenance during off-peak hours is not to be included in the calculation of system availability. The Selected Offeror is to provide a system to monitor and report on responses as defined and approved by the Authority. All metrics are to be measured and evaluated in hours. Downtime. Downtime is to be defined as the term during which any core functionality of the Individual Exchange is not functioning/available due to network, hardware, operating system or application program failure and there are no workarounds. Scheduled maintenance (within the defined maintenance window), approved by the Authority, does not count towards downtime. System availability is to be based on the following hours of operation: Individual Exchange Hours of Operation. Individual Exchange access is to be available at a minimum of 99.9% of the expected operational time, twenty-four (24) hours per day, seven (7) days per week. The Contractor is to ensure system availability meets the following performance standards: | Up to 6% of the monthly operating fee, as follows: Any 1 of 4 not met: 1% Any 2 of 4 not met: 3% Any 3 of 4 not met: 5% Any 4+ not met: 6% |
| 1. Production Downtime. Maximum monthly production downtime for all core Individual Exchange components is to be no more than four hours per month, excluding downtime events that are external to the Selected Offeror. |  |
| 2. Network Connectivity Downtime. Selected Offeror network connectivity downtime for all core Individual Exchange components, is to be no more than one (1) hour per month. This downtime will be included in the overall production downtime figures and not to be considered additive. |  |
| 3. Scheduled Maintenance. Scheduled maintenance for all Individual Exchange components, is to be no more than ten (10) hours per month (and within the defined maintenance window(s) as approved by the Authority – a corresponding technical change request needs to be submitted first for the Authority’s approval). |  |
| 4. System and Application Availability – Systems and applications shall be available 99.9% of the time, excluding scheduled maintenance. |  |

| 2. Service Level Agreement – System Performance |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| System performance is to be defined as Individual Exchange response time to user portal queries, (the portal is operational twenty-four (24) hours a day, seven (7) days a week). The Selected Offeror is to provide a system to monitor and report on responses as defined and approved by the Authority. All metrics are to be measured and evaluated in seconds. The Selected Offeror is to ensure system performance meets the following performance standards: | Up to 6% of the monthly operating fee, as follows: Any 1 of 4 not met: 1% Any 2 of 4 not met 3% Any 3 of 4 not met: 5% All 4 not met: 6% |
| 1. Record Search and Retrieval Time. Within four (4) seconds 95% of the time, where record retrieval time is defined as the time elapsed after the retrieve command is entered until the record data loads to completion on the monitor. |  |
| 2. Screen Edit Time. Within four (4) seconds 95% of the time, where screen edit time is defined as the time elapsed after the last field is filled on the screen with an enter command until all field entries are edited with errors highlighted on the monitor. |  |
| 3. New Screen/Page Time. Within four (4) seconds 95% of the time, where new screen/page time is defined as the time elapsed from the time a new screen is requested until the data from the screen loads to completion on the monitor. |  |
| 4. Web Portal Response Time. Within four (4) seconds 99% of the time, where Web Portal response time is defined as the time elapsed from the command to view a response until the response appears or loads to completion on the monitor. |  |

| 3. Service Level Agreement – Database Updates |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| Database updates are to be defined as the activities necessary to maintain current and accurate data as required to conduct the functions outlined in this RFP, in compliance with all requirements herein. The Authority and the Selected Offeror will develop appropriate data quality metrics to support these SLAs. The Selected Offeror is to ensure database update activities meet the following performance standards: | Up to 5% of the monthly operating fee, as follows: Any 1 of 3 not met: 1% Any 2 of 3 not met 3% Any 3+ not met: 5% |
| 1. Database Updates and Data Synchronization. All databases, including Disaster Recovery, must be updated and synchronized no less than daily. |  |
| 2. Data Delivery. 99.9% of data must be delivered accurately and per business logic developed in the application. |  |
| 3. Transaction Completion. 99.9% of system transactions must be completed accurately and per business rules developed in the application. |  |
| 4. Batch Jobs - Contractor shall run all assigned batch jobs at the predefined scheduled time frame(s) unless otherwise instructed by the Authority. Batch jobs should be completed 99.9% during the predefined windows |  |

| 4. Service Level Agreement – Operational Problem Management |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| Provide individual operational problem management for issues as they occur during the Maintenance & Operations phase of the project, including problems associated with all system components outlined in this RFP. Operational issues are to be classified, communicated to the Authority, documented, addressed and tracked. The Selected Offeror is to provide software tools to enable the tracking of a specific defect from identification through correction, including all testing performed to ensure the correct fix is in place. Issues are to be documented in the Contractor-specified format, if approved by the Authority. During the Maintenance & Operations phase the Selected Offeror is to categorize and resolve errors in accordance with the Authority problem management standards provided by the Authority, as follows: | Up to 6% of the monthly operating fee, as follows: Priority 1 Errors standard not met: 3% Priority 2 Errors standard not met 1.25% Priority 3 Errors standard not met: 1.25% Priority 4 Errors standard not met: 0.50% |
| Priority 1 Errors. Critical business impact. Indicates core functionality of the SBE is unavailable for use resulting in a critical impact on operations. Requires immediate the Authority notification, half-hour updates and resolution within two (2) hours. |  |
| Priority 2 Errors. Serious business impact. Indicates serious production issues where core functionality of the Individual Exchange is available but is severely limited and no workaround or a complicated workaround exists. Requires immediate Authority notification, hourly updates and resolution within four (4) hours. |  |
| Priority 3 Errors. Moderate business impact. Indicates moderate production issue where core functionality of the SBE is usable but a workaround is available (not critical to operations). Requires immediate notification to the Authority, two (2) hour updates, and resolution within twelve (12) hours. |  |
| Priority 4 Errors. Minimal business impact. Indicates the problem results in little impact on operations or a reasonable circumvention to the problem has been implemented. Requires immediate notification to the Authority notification with updates and resolution within an agreed-upon schedule between the Selected Offeror and the Authority (as defined by the Authority). |  |
| Help Desk call wait time - At least 99% of help desk calls are answered in 2 minutes or less |  |
| Support calls for Priority Levels 1&2 call back time – Selected Offeror must respond back to the Authority in: - 30 minutes or less from the time the Priority 1 support call was made. - 60 minutes or less from the time the Priority 2 support call was made. |  |

| 5. Service Level Agreement – Consumer Engagement, Contact Center, Mail Room |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| The Selected Offeror is to provide customer service support. The Selected Offeror is to maintain sufficient staff and systems to manage, track and report on Customer Services via multiple channels, including telephone, web portal, e-mail, and web chat. The Selected Offeror is to provide an integrated contact management system to be used in tracking and managing Customer contacts from all channels, and can report on Customer contact metrics separately. Customer Service support is to be available 100% of the time during Standard working hours, as specified by the Authority. The Selected Offeror is to ensure customer service support meets the following performance standards: |  |
| Achieve a monthly average first encounter resolution rate of a minimum of 75%. First encounter resolution is defined as encounter resolved by a Customer Service Representative rather than those routed to a supervisor or requiring a follow-up Customer contact. | $5,000 when monthly average first Encounter resolution rate falls below 75%. |
| Maintain a maximum monthly average time-to-answer of 60 seconds. | $5,000 for monthly average time-to-answer exceeding 60 seconds. |
| Maintain a monthly average percentage of calls answered in 30 seconds or less at seventy percent (70%) or higher. | $2,500 when monthly percentage of calls answered in 30 seconds or less falls below 65%. |
| Maintain a maximum monthly average abandoned call rate of three (3) percent, excluding calls where a caller left a message and calls that were abandoned before 30 seconds. | $2,500 for monthly average abandoned call rates exceeding 3% or $5,000 for monthly average abandoned call rates exceeding 5%. |
| Maintain a maximum time-to-answer of 2 minutes. | $2,500 if 10% or more of calls exceed given threshold over a period of a month on average. $5,000 if 30% or more of calls exceed given threshold. |
| Respond to all chat messages within 30 seconds. | $2,500 when monthly percentage of chats answered in 30 seconds or less falls below 85% |
| Respond to all emailed inquiries received to within one (1) Business Day. | $5,000 for monthly average time-to-respond exceeding one (1) Business Day. |
| Receive a top two rating (assuming a five-point scale) in 85% of total Customer surveys for Customer satisfaction on the Authority-approved Customer surveys. | $2,500 when quarterly average overall Customer satisfaction scores are less than 85%. $5,000 for each instance when quarterly average overall Customer satisfaction scores are less than 75%. |
| Scan and triage paper applications, Attestations and other Eligibility-related documentation within one (1) Business Day as measured by the time of receipt such documentation. | $5,000 if less than 99% of all paper applications, Attestations and other Eligibility-related documentation are not scanned and triaged within one (1) Business Day as measured over one month. |
| Process at least 80% of all Eligibility documentation, Eligibility verifications for Individuals and Redeterminations within two (2) Business Days as measured from the time of receipt of application containing complete information. 100% of documentation related to Eligibility verifications and Redeterminations shall be processed within three (3) Business Days. | $5,000 if 100% of Eligibility documentation, Eligibility verifications and Redeterminations are not processed within three (3) Business Days on average over a month |
| 80% of all Enrollment forms must be processed within two (2) Business Days as measured from the time of receipt of the Enrollment forms containing complete information. 100% of Enrollment forms shall be processed within three (3) Business Days. | $5,000 if 100% of Enrollment forms are not processed within three (3) Business Days. |
| Process completed Enrollment forms received with a minimum of 99% accuracy. | $5,000 when monthly average falls below 99%. |
| Process Enrollment data provided to Exchange systems with a minimum of 98% accuracy. | $5,000 when monthly average accuracy rate falls below 98%. |
| Send transfers / referrals to Medical Assistance from point of determination Process transfers / referrals from Medical Assistance from point of receipt | $10,000 when monthly average rises over 5 business days |

| 6. Service Level Agreement – Noticing, Reporting, Financial Operations |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| The Selected Offeror is to ensure customer service support meets the following performance standards for Noticing, Reporting, and Financial Management Operations: |  |
| Send 98% of notifications of successful Enrollment to Qualified Individual or Subscriber, unless otherwise designated by the Qualified Individual | $2,500 when monthly average of Enrollment notifications sent is below 98%. |
| Send 100% of Renewal, Redetermination and Open Enrollment notices in accordance with the timelines set forth in the Authority's policies and procedures. | $100 per statement up to a maximum per day of $5,000 per day for each Business Day that Renewal, Redetermination or Open Enrollment notices are sent late. Monthly maximum of $10,000 |
| Send Qualified Individual exception requests and supporting documents, Encounter logs and Encounter transcripts to the Authority, 70% within three (3) Business Days of receipt of the Qualified Individual written Exception request and 100% within four (4) Business Days of receipt of the Qualified Individual written Exception request. | $1,000 when monthly average falls below 70% within 3 Business Days or 100% within 4 Business Days. |
| Meet the following service levels for Reports: Daily reports are due to the Authority by 12pm the following Business Day. Weekly reports are due to the Authority by the second (2nd) Business Day following the end of the reporting period. Financial Monthly reports are due to the Authority by third (3rd) Business Day following the end of the reporting period with the exception of the disenrollment for non -payment of premium notice report, which is due on the first (1st) Business Day of the month following the end of the month. Quarterly reports are due by the fifteenth (15th) Business Day following the end of the reporting period. Semi-annual reports are due by the twentieth (20th) Business Day of the end of the reporting period. Annual reports are due by the twenty-fifth (25th) Business Day following the end of the reporting period. | $200 for each Business Day beyond the due dates for each listed report. Monthly maximum of $5,000. |
| Provide accurate reports. If the Authority identifies a substantive problem (i.e. such report contains incorrect data or is not presented in a mutually agreeable format) with the content of any report delivered by the Contractor resulting in the report needing to be regenerated, the Contractor must produce a corrected report within one (1) Business Day. | $100 for each additional Business Day the corrected report is delivered within one Business Day. Monthly maximum of $5,000. |
| Meet the following service levels for incident and management reporting: Provide incident and management reports using a Authority defined template no later than 5:00 p.m. of the day on which the Selected Offeror discovers any problem, which may jeopardize the success or timely completion of any of its responsibilities under the Agreement, if the incident is identified prior to 4:30 p.m. on any Business Day, and no later than 9:30 a.m. on the next Business Day if the incident is identified after 4:30 p.m. All incidents that are not fully resolved in one (1) Business Day are supplemented with email updates every Business Day by 5:00 p.m. during incident remediation. Provide the final incident report to the Authority within two (2) Business Days of resolving the issue that caused the incident. Provide written management reports in response to particular issues within two (2) Business Days of the Authority’s request. | $100 for each instance of violating incident report timing parameters. If in the course of investigating the incident, it is determined that the Contractor did not inform the Authority in a timely manner, the Contractor shall incur an additional penalty of $500 per incident. Monthly maximum of $5,000. |
| Perform monthly reconciliation of the Authority receivables. The reconciliation and all documentation in support of this reconciliation will be submitted to the Authority no later than thirty (30) Calendar Days following month end. | $1,000 per Business Day for each Business Day beyond the due date. Monthly maximum of $10,000. |
| Monthly billing must occur on schedule as defined by the Authority and Contractor. | $1,000 per day beyond scheduled date, capped at $5,000 per month. |
| Statements must accurately reflect amount owed per subscriber’s plan selection for self and all dependents. The subsidy must also be calculated correctly and deducted from the premium due. | $50 per inaccurate statement, capped at $1,000 per month. |
| Monthly Delinquency and Termination notices must occur on schedule as agreed upon by the Authority for both subsidized and non-subsidized individuals as defined by the Authority. | $100 per statement up to a maximum per day of $2,500 for each Business Day that Notices are sent late. Monthly maximum of $5,000. |
| Premium Remittance and Reporting (EDI 820) must occur on schedule as defined by the Authority and Selected Offeror. | $1,000 per day beyond scheduled date, capped at $5,000 per month |
| Carrier 820 discrepancies must be resolved within 3 business days of carrier notification of discrepancy | $100 per discrepancy, capped at $1,000 per 820 process |
| Refunds for eligible accounts must be defined and processed on a weekly basis as defined by the Authority and Selected Offeror | $500 per day beyond scheduled date, capped at $2,500 per month |
| Month-end financial reports must report accurately on the ending Accounts Receivable due from subscribers, Accounts Payable due to carriers, and Premium Register, which lists all premiums billed in the current month billing cycle. These reports must reconcile to the cash balance in the Authority’s bank account. Financial reports must be available by the third business day following the end of the month. Daily Financial Management reports must include a daily deposit detail breakdown, listing all payments by subscriber. All reports must indicate the carrier that is associated with the subscriber’s invoice amount. | $200 for each Business Day beyond the due dates for each listed report; $500 for any identified inaccuracies up to a total of $2,500 per month. |

| 7. Service Level Agreement – Privacy and Security |  |
| --- | --- |
| Key Performance Indicator | Liquidated Damages |
| Failure to notify the Authority in a timely manner per Appendix B – A.5. | $1,000 per day beyond notification requirements, capped at $10,000 per month. |
| Failure to deliver a report per Appendix B – A.5. | $1,000 per day beyond notification requirements, capped at $10,000 per month. |
| Failure to complete and submit to the Authority required federal documents (MARS-E 2.0) in a timely manner to ensure initial ATC. The documentation will include: System security plan Plan of action and milestones, and Provide documentation and support to execute Interconnection Security Agreement (ISA) with CMS. | $1,000 per day beyond the required due date for the initial filing and any subsequent years filing, capped at $10,000 per month. |
| Failure to remediate security or privacy risk within agreed upon timeframe as outlined in POAM or Corrective Action Plan. | $1,000 per day delayed in correcting or remediating systems responsible for incident, capped at $10,000 per month. |
| Privacy or Security breach caused or failed to be prevented by the Offeror that impacts the Authority’s customers | As necessary, HIPAA privacy or security penalties, as relevant. |

The parties agree to the following limitations to Service Level Agreements and Associated Liquidated Damages:

- The liquidated damages would be counted towards the overall cap on liabilities or other remedies under the Agreement;

- Total liquidated damages in any given month associated with the failure to meet SLAs shall not exceed 35% of monthly M&O fee;

- If the same event (such as unavailability of a portal) gives rise to more than one application of liquidated damages, the Authority shall elect to assess only the greater of the Liquidated Damages amount against Contractor;

- Contractor shall not be responsible for delays or business operation issues caused by circumstances beyond Contractor’s control or the delays not directly attributable to Contractor.

Additionally, liquidated damages will be in effect in the third month after Go-live.

SLAs and associated liquidated damages shall be reviewed annually and modified as agreed by the parties.

ATTACHMENT G:  IRAN FREE CERTIFICATION FORM

The Iran Free Certification Form may be found at:

http://www.puc.state.pa.us/General/pdf/RFP/RFP-1-2019_AppC_IranFree_Procurement_Certification_Form.pdf

It is strongly recommended that Offerors send the proposal submission email requesting a “Delivery Receipt” and “Read Receipt” and send the proposal sufficiently in advance of the deadline to be able to confirm receipt within the deadline and to be able to remediate transmission problems should they occur.