## Instructions
Instructions:
1. On the Implementation Phase tab please enter the dollar amount in the yellow cell for each Milestone deliverable.
The amount entered may not exceed the allowable percentage of the total DDI cost for that Milestone deliverable.
A 5% withhold will be applied to each Milestone deliverable which will be payable after six continuous months of M&O.
2. On the M&O Phase tab please enter the monthly dollar in the yellow cell for each Operation Year.
The annual amount for each Operation Year will automatically compute.
3. On the Enhancement Phase tab please enter the hourly rate for each contact year.
The hourly rate will automatically be calculated for 5,000 hours.
The enhancment hours are cumulative and unused hours carry over to the next contract year.
4. The Master tab will carry over the values from the Deliverable Phase, M&O Phase, and the Enhancement Phase.
The cells are locked and may not be manually entered.
5. The Payable Events tab shows the events for each phase. The events must be completed prior to payment.
6. The Project Timeline is a representation of the proposed timeline. The timeline is a representation of the proposed time to complete the project.
Payment will only be made after each phase is completed as described in the RFP.
7. The Example Deliverable Phase tab represents a completed tab. The values used in the Example tab are purely shown as sample values.
It does not represent the Commonwealth's expected cost.
8. The Subcontractor's monetary value based off of the SDB/VBE Participation Goals (listed in Section #13 of the RFP JAGGAER Desctiption) will be determined by the Contract Total listed in the "EVV Module Total Cost Summary Table" under the "Master" tab.

## Master
RFP 15-23: Electronic Visit Verification Module
Offeror Name:
Offeror SAP Vendor Number:
EVV Module Total Cost Summary Table
Cost Summary Tables | Base Years
Deliverable Phase | 0
M&O Phase | 0
Enhancement Phase | 0
Contract Base Year Total | 0
Option Year 1 | 0
Option Year 2 | 0
Option Year 3 | 0
Option Year 4 | 0

## Implementation Phase
Deliverable Payment Table- Milestone Phase Execution Deliverables- Subject to Withhold
RFP Reference | Milestone Phase Execution/Material Services Description | Payable Event** | Maximum Allowable Pecentage of Total DDI Cost | Total Fixed Execution Cost | Percentage of Total DDI Cost*** | Initial Payable Amount | Withhold Payable*
Section I-7.A.1 through 6. | Initiation Phase | Upon successful completion and Department approval of Section I-7.A.1 through 6. activities. | 5% |  | 0% | 0 | 0
Section I-7.B. | Requirements Phase | Upon successful completion of Joint Application Design session and appoval by the Department of the Business Requirements Document. | 5% |  | 0% | 0 | 0
Section I-7.C. | Design Phase | Upon successful completion and appoval of the Systems Requirements Document and the System Design Document by the Department. | 10% |  | 0% | 0 | 0
Section I-7.D.1 through 2. | Development Phase | Upon successful completion of all Data Conversion and Sprint Sessions and the Department approves the start of User Acceptance Testing. | 20% |  | 0% | 0 | 0
Section I-7.E. | Testing Phase | Upon successful completion of User Acceptance Testing, Performance testing, load testing, Parallel Testing, Data Migration, and Security testing. | 20% |  | 0% | 0 | 0
Section I-7.F.1 through 4 | Implementation Phase | Upon successful implementation of the EVV Module and month of successful operation in the production environment with all defects cured. | Up to 100% |  | 0% | 0 | 0
|  | Total Milestone Execution Deliverables (Subject to Withhold) |  | 0
NOTES:
* Payable after 6 months after implementation provided CMS Certification is maintained.
** See Detail on Payable Events Tab
*** If the Percentage of Total DDI Cost is above the maximum allowable percentage the cell will be shaded red.

## Example Implementation Phase
Deliverable Payment Table- Milestone Phase Execution Deliverables- Subject to Withhold
RFP Reference | Milestone Phase Execution/Material Services Description | Payable Event** | Maximum Allowable Pecentage of Total DDI Cost | Total Fixed Execution Cost | Percentage of Total DDI Cost | Initial Payable Amount | Withhold Payable*
Section I-7.A.1. through 6. | Initiation Phase | Upon successful completion and Department approval of Section I-7.A.1 through 6. activities. | 5% | 50 | 5% | 47.5 | 2.5
Section I-7.B. | Requirements Phase | Upon successful completion of Join Appication Design session and appoval by the Department of the Business Requirements Document. | 5% | 50 | 5% | 47.5 | 2.5
Section I-7.C. | Design Phase | Upon successful completion and appoval of the Systems Requirements Document and the System Design Document by the Department. | 10% | 100 | 10% | 95 | 5
Section I-7.D. | Development Phase | Upon successful completion of all Data Conversion and Sprint Sessions and the Department approves the start of User Acceptance Testing. | 20% | 200 | 20% | 190 | 10
Section I-7.E. | Testing Phase | Upon successful completion of User Acceptance Testing, Performance testing, load testing, Parallel Testing, Data Migration, and Security testing. | 20% | 200 | 20% | 190 | 10
Section I-7.F. | Implementation Phase | Upon successful implementation of the EVV Module and month of successful operation in the prodcution enrionment with all defects cured. | Up to 100% | 400 | 40% | 380 | 20
|  | Total Milestone Execution Deliverables (Subject to Withhold) |  | 1000
|  | ** See Detail on Payable Events Tab |  |  |  |  | * Payable after 6 months after implementation provided CMS Certification is maintained.

## M&O Phase
Maintainance and Operation Full Year* | Monthly Cost | Yearly Cost
Operations Year 1: |  | 0
Operations Year 2: |  | 0
Operations Year 3: |  | 0
Operations Year 4: |  | 0
Operations Year 5: |  | 0
Operations Optional Year 1: |  | 0
Operations Optional Year 2: |  | 0
Operations Optional Year 3: |  | 0
Operations Optional Year 4: |  | 0
Total Base Term Cost |  | 0
| Total 9 Year Cost | 0
* Operations Year 1 begins on the 1st Calendar Day after the EVV Module is implemented.

## Enhancement Phase
Contract Year | Hourly Rate | Hours Available* | Total for Year
Contract Year 1 |  | 5000 | 0
Contract Year 2 |  | 5000 | 0
Contract Year 3 |  | 5000 | 0
Contract Year 4 |  | 5000 | 0
Contract Year 5 |  | 5000 | 0
Option Year 1 |  | 5000 | 0
Option Year 2 |  | 5000 | 0
Option Year 3 |  | 5000 | 0
Option Year 4 |  | 5000 | 0
Total Base Term Cost |  |  | 0
Total 9 Year Cost |  |  | 0
* Unused Hours Carryover to next contract year.

## Payable Events
Responsibility | Category | Initiation Phase
PMO | Project Scope | Prepare Project Scope.
Vendor/PMO |  | Review Project scope with PMO.
Vendor/PMO |  | Walk through Project Scope with Department.
Department |  | Department approves Project Scope.
Vendor | IMS Initial Project Plan | Develop Initial Project Plan for IMS.
Vendor/PMO |  | Review Project Plan with PMO.
Vendor |  | Walk through Project Plan with Department.
Department |  | Department approves Project Plan.
Vendor/PMO |  | Baseline project plan and integrate into the IMS.
Vendor |  | Update project plan weekly throughout the course of the Project.
Department | SharePoint | Develop location on the Departments MMIS Project SharePoint.
PMO | Project Notebook | Create the EVV Project Notebook and update weekly throughout the project.
Vendor/Department | Week/Monthly Reporting | Initiate Weekly and Monthly Reporting to Department.
Vendor/PMO | Vendor Onboarding Training | Attend PMO led training on the following:
Vendor/PMO |  | Train Vendor on Integrated Master Schedule (IMS) for use in module implementation.
Vendor/PMO |  | Train vendor on SharePoint.
Vendor/PMO |  | Train on Azure DevOps used for tracking requirements.
Vendor/PMO |  | Change Control Board Overview and Procedures.
Vendor/PMO |  | Risk and Issues Plan Overview and Procedures.
Vendor/PMO |  | Defect Management Plan Overview and Procedures.
Vendor/PMO |  | Document Management Plan Overview and Procedures.
Vendor/PMO |  | Communication Plan Overview and Procedures.
Vendor/PMO |  | SMC Certification Plan Overview and Procedures.
Vendor/PMO |  | Training Plan Overview and Procedures.
Vendor/PMO |  | Data Management Strategy Plan Overview and Procedures.
Vendor/PMO |  | Implementation Plan Overview and Procedures .
Vendor | Vendor Payment | Vendor sends payment request showing all vendor task in the Initiation Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Responsibility | Category | Requirements Phase
Vendor | Business JADs | Review RFP requirements.
Vendor/PMO |  | Determine JADs topics with PMO and Schedule for JADs.
ALL |  | Walk through with Department on JADs topics and identify required stakeholders.
Department |  | Department approves topics, schedule, and stakeholders.
PMO |  | Schedule JADS and notify stakeholders.
PMO |  | Update IMS Project Plan with JADs topics and schedule.
ALL |  | Conduct JADs.
Vendor/PMO | Environments | Identify Environments and plan when environments are implemented with PMO.
Vendor |  | Walk through of planned environments with Department.
Vendor/PMO |  | Update IMS with Environment implementation dates.
Vendor | BRD | Review and provide feedback on the PMO produced BRD.
PMO |  | Walk through of BRD with Department.
Department |  | Department approves the BRD or returns for rework.
PMO |  | Finalize BRD requirements in ADO.
Vendor/PMO | Update IMS | Prepare Baselined Project Plan in IMS based on updates from Requirements Gathering.
Vendor |  | Walk through baseline project plan with Department.
Department |  | Department approves Baseline Project Plan - Changes can only be made through CCB.
Vendor | Vendor Payment | Vendor send written payment request showing all vendor task in the Requirement Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Responsibility | Category | Design Phase
Vendor/PMO | Technical JADs | Determine technical JADs topics with Legacy MMIS contractors.
Vendor/PMO |  | Review JADs topics with PMO and Schedule sequence for technical JADs.
Vendor/Department |  | Walk through with Department on technical JADs topics andiIdentify required Stakeholders.
Department |  | Department approves topics, schedule, and stakeholders.
PMO |  | Schedule technical JADS and notify stakeholders.
Vendor |  | Update IMS Project Plan with JADs topics and schedule.
Vendor |  | Vendor leads technical JADs sessions with PMO assistance.
ALL |  | Conduct and complete technical JADs.
Vendor/PMO | SRD | Attend PMO Led Training on SRD.
Vendor/PMO |  | Prepare SRD in approved template for PMO review.
Vendor/Department |  | Walk through of SRD reviewed by PMO with Department.
Department |  | Department approves SRD or returns for rework.
Vendor |  | Enter System Requirements in ADO.
Vendor/PMO | SDD | Attend PMO Led Training on SDD.
Vendor/PMO |  | Prepare SDD in approved template for PMO review.
Vendor/Department |  | Walk through of SDD reviewed by PMO with Department.
Department |  | Department approves SDD or returns to vendor for rework.
Vendor/PMO | Data Conversion Plan | Prepare Data Conversion Plan for PMO review.
Department |  | Present PMO reviewed Data Conversion Plan to the Department.
Department |  | Department approves Data Conversion Plan or returns to vendor for rework.
Vendor/PMO |  | Enter Data Conversion Task, Milestones with dates as approved by the Department in IMS.
Vendor | Vendor Payment | Vendor send written payment request showing all vendor task in the Design Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Responsibility | Category | Development Phase
Vendor | DEV and SIT Environments | Vendor implements DEV and SIT Environments.
Vendor |  | Walk through of DEV and SIT Environments with legacy vendors, PMO, and Department.
Department |  | Department approves DEV and SIT Environments or request vendor rework.
Vendor | Sprints | Vendor leads walkthrough of proposed Development Phase task and activities.
Department |  | Department approves proposed Development Phase or returns to vendor for rework.
Vendor |  | Develop Sprints topic, sequence, and timing for PMO review.
Vendor/PMO/Dept |  | Present PMO Sprint schedule, process, and attendees to the Department.
Department |  | Department approves Sprint schedule or returns to vendor for rework.
Vendor |  | Enter Sprints in Project Plan in IMS.
All |  | Begin two week sprints.
Vendor |  | Vendor prepares walk through of each completed two week Sprint.
Department |  | Department approves each two week Sprint is completed or returns to vendor for rework.
Vendor |  | Sprints are successfully completed.
Vendor | Vendor Payment | Vendor send written payment request showing all vendor task in the Design Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Responsibility | Category | Testing Phase
Vendor/PMO | SIT Testing Plan | Prepare Test Plan for PMO review.
Vendor |  | Present PMO reviewed Test Plan to the Department.
Department |  | Department approves Test Plan or returns to vendor for rework.
Vendor |  | Enter Testing Task, Milestones with dates with dates as approved by the Department in IMS.
Vendor/PMO/Dept |  | Confirm Project Plan in IMS is correct and Department approves or returns for rework.
Vendor/PMO | SIT Execution | Create SIT Plan for PMO Review.
Vendor/PMO/Dept |  | Review the SIT Plan with the Department.
Department |  | Department approves SIT Plan.
Vendor |  | Vendor identifies qualified testers who are not on the vendor's development team.
Vendor |  | Walk through of vendor's testing team.
Department |  | Department approves vendor's testing team or request rework.
Vendor/PMO/Dept |  | Execute SIT Plan.
Vendor/PMO |  | Evaluate SIT Plan.
Vendor/PMO/Dept |  | Walk through of SIT Results.
Department |  | Department approves SIT results or request more testing.
Vendor |  | Vendor implements UAT and Training Environments.
Vendor/PMO/Dept |  | Walk through of UAT and Training Environments with legacy vendors, PMO, and Department.
Department |  | Department approves UAT and Training Environments or request vendor rework.
PMO | UAT Test Plan and Test Data | Create a comprehensive UAT Test Plan for the EVV Initial Implementation.
PMO |  | Review the UAT Test Plan with the Department.
Department |  | Department approves UAT Test Plan.
Vendor/PMO/Dept |  | Create nonidentifiable Test Data database for use throughout Testing.
Vendor/PMO |  | Walk through of Test Data.
Department |  | Department approves Test Data or request rework.
Department | Execute UAT Testing | Department identifies internal Testers.
All |  | Execute Testing.
Vendor/PMO/Dept |  | Final Walk through of Testing Phase.
Department |  | Department approves Testing then approves initiating implementation.
Vendor | Vendor Payment | Vendor send written payment request showing all vendor task in the Testing Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Responsibility | Category | Implementation Phase
Vendor/PMO | Production and Disaster Recovery Environments | Vendor implements Production and Disaster Recovery Environments.
Vendor/PMO/Dept |  | Walk through of Production and Disaster Recovery Environments with legacy vendors, PMO, and Department.
Department |  | Department approves Production and Disaster Recovery Environments or request vendor rework.
Vendor/PMO | Training | Develop Training Plan for integral and external users.
Vendor/PMO |  | Walk thorough Training Plan with Department.
Department |  | Department approves Training Plan and identifies training stakeholders or request rework.
Vendor/PMO/Dept |  | Schedule required training.
PMO |  | Update IMS with scheduled training.
Vendor/PMO/Dept |  | Execute Training.
Vendor/PMO | Implementation Planning | Create Release Plan and review with PMO.
Vendor/PMO/Dept |  | Walk through of Release Plan with Department.
Department |  | Department approves Release Plan or request rework.
Vendor/PMO |  | Create Implementation Plan and Checklist and review with PMO.
Vendor/PMO/Dept |  | Walk through of Implementation Plan and Checklist with Department.
Department |  | Department approves Implementation Plan and Checklist.
All | Implementation | Implementation.
Vendor | Vendor Payment | Vendor send written payment request showing all vendor task in the Implementation Phase are completed.
Department |  | Department approves payment or notifies vendor of missing task.
Maintenance and Operation Phase
Vendor | Vendor Payment | Submit monthly invoice to the Department.
Department |  | Pays vendor upon successful submission of invoice.

## Project Timeline
Project Phase | Months after Contract is Effective
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Initiation Phase
Requirements Phase
Design Phase
Development Phase
Testing Phase
Implementation Phase
Maintenance and Operation Phase
Project Phase | Months after Contract is Effective
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Initiation Phase
Project Scope
IMS Initial Project Plan
SharePoint
Project Notebook
Week/Monthly Reporting
EVV Vendor Onboard Training
EVV Vendor Payment
Requirements Phase
Business JADs
Environments
BRD
Update IMS
EVV Vendor Payment
Design Phase
Technical JADs
SRD
SDD
Data Conversion Plan
EVV Vendor Payment
Development Phase
Dev and SIT Environment Live
Sprints
EVV Vendor Payment
Testing Phase
SIT Testing Plan
SIT Execution
UAT Test Plan and Test Data
Execute UAT Testing
EVV Vendor Payment
Implementation Phase
Training, Prod and DR Environments
Training
Implementation Planning
Implementation
EVV Vendor Payment
Maintenance and Operation Phase
Withhold Vendor Payment